Surrey Declaration & Action Plan

Mental Health Crisis Care Concordat

Surrey Mental Health Crisis Care Concordat – Action Plan to enable delivery of shared goals

| Commissioning to allow earlier intervention and responsive crisis services |
| --- |
| No | Action | Timescale | Led By | Outcomes |
| GOVERNANCE |
| 1 | Delivery group established - meet monthly to oversee the action plan and ensure delivery | July 2014 | CCG | Transformation of local services |
| 2 | Sign off declaration/action plan | September 2014 | Delivery Group | Commitment given by all agencies to deliver |
| 3 | Practitioner group established reporting to the strategic delivery group where operational issues can be escalated for resolution | September 2014 | SABP | Ensure there are escalation processes for unresolved issues |
| 4 | Joint SI & Safeguarding Learning -Triangulation of different agencies MH SI/Safe G reporting and review processes | June 2015 | Delivery Group | Shared learning from SI’s to improve future practice |
| 4a | Review of safeguarding in all substance misuse contracts/providers | End Sept | Public Health- Catherine Croucher | Commissioners are assured of the safeguarding capabilities of substance misuse service providers |
| 5 | Outcome Metrics - An agreed joint data set to establish baseline and capture demand and responses for people in mental health crisis (SABP, EDT, Police, 136, Ambulance, A&E’s, 111) | July 2014 | NHSE & Delivery Group | Clearer evidence and a focus on outcomes on which to base local commissioning and ensure inequalities addressed |
| 6a | Clarify with Police toolkit and definition around intoxication in relation to 136 | Sept 14 | Public Health- Martyn Munroe | Define if data capture will be on presenting intoxication or ‘history’ to better understand needs |
| 42- NEW April 15 | Ensure an appropriate assessment process for threshold around drugs and alcohol in S136 Guidance. | MM to discuss with Surrey Police to determine appropriate and reviewed thresholds by May 2015. | Public Health (Substance Misuse)- Martyn Munroe | Ensuring appropriate use of 136 and supporting diversion to supportive service that meet the person’s needs. |
| RESOURCE |
| 6 | Right Level of Beds Commission Mental Health Strategies to complete simulation modelling on Surrey MH Crisis model to meet needs | July – Dec 2014 | CCG | Least restrictive most local and effective response to crises. Prevention of out of area and custody placements |
| 6a | Need to ensure that CAMHS beds and pathway is included in approach and consideration understood as to any impact. | End Oct | CAMHS Diane McCormack | Simulation modelling is for Adult services but need to understand any potential impact |
| 7 | Gap Analysis Analysis of gap between current provision and concordat vision to inform actions | September 14 | NHSE & Delivery Group | Focus commissioning support programmes on areas needing improvement |
| CONSISTENT RESPONSE |
| 8 | Joint protocols Develop and agree local standards and protocols being clear for each partner agency response times, roles and responsibilities | March 2015 | Transport SECAMB A&E – Acutes MisperPolice Restraint and Search-SABP |  |
| 8a | sign off current reviewed protocols from all agencies | End August 14 | All agencies/practitioner group | Understand if protocols are already in place and if they are being applied at the ground level |
| 9 | Training Joint Training developed delivered to increase mental health awareness and inform about local standards and protocols for frontline emergency service responders | Pack developed April – June 2015 Delivered July 2015 – March 2016 | Joint Training Group | Staff are equipped to treat mental and physical conditions with equal priority |
| 9c | Public Health enters mobilisation for a new Tier 3 and 4 provider for substance misuse Oct 2014 as part of which an operation guidance document will be produced | Development and implementation Q3 and Q4 Delivery as core practice from Q1 2015/16 available to Crisis Concordat Group 01/04/15 Cascade to all care planned substance misuse service providers in Q1, deliverable from Q2 | Public Health- Martyn Munroe | To provide clear, updated guidance to promote commissioning practice in line with concordat expectations. |

| Access to support before crisis point: – “know who to contact at any time, 24 hours a day, seven days a week” |
| --- |
| No | Action | Timescale | Led By | Outcomes |
| 10 | Primary care support on early identification of mental health issues and referral points | Nov 14 | CCG’s | Early identification and crisis prevention |
| 10a | Identified primary care development measures within the “quality and innovation” measures in Public Health Substance Misuse contracts (similar to CQUIN) scheduled for 2015/16 Further opportunities are available to pick this up under “quality and innovation” measure and within the operational guidance. | Plan Development Q3 and Q4 14/15 delivery synchronised engagement with GP practices Q1-Q4 2015-16 | Public Health- Martyn Munroe | Prevention of avoidable crises. |
| 11 | Development of local planning for integrated community hubs inclusive of mental health and responding to inequalities in access to services and aligning MH hours of service to those in primary car | CCG specific through 15/16 | CCG’s | Improved outcomes and experiences of people with mental health needs accessing services meeting their whole needs and ensure services take account of the needs of diverse local populations when improvements are made |
| 12 | Development of voluntary sector at a local level to provide peer and carer support services such as buddying and safe havens in each locality | April – June 2015 | SCC/CCGs | Improved community response should have impact on improving service user and carer experience being able to reduce usage of in-patient facilities in mental health and acute hospital presentation. |
| 13 | Commission, deliver and evaluate suicide prevention training to key front line professionals. | March 2015: 1 safeTALK session per CCG area plus 1 ASIST course. March 2016: 9 SafeTALK, 3 ASIST, 2 SafeTALK train the trainer places | Public Health- Catherine Croucher | To reduce the number of suicides and attempted suicides across Surrey. |
| 13a | Based on the results of an evidence review and audit of self-harm A&E attendances, develop actions that aim to improve the current management and prevention of self-harm. | Dec 14: Evidence Review A&E Audit: TBC Actions: March 2016 | Public Health- Catherine Croucher | To prevent and reduce the impact of self-harm. |
| 13b | Find out how learning from SUIs conducted within secondary care, mental health services and primary care is disseminated and acted upon. | Feb 2015 | Public Health- Catherine Croucher | Gain an understanding of the learning from Serious Untoward Incident investigations for suspected suicides. |

| Urgent and emergency access to crisis care: – “treated with as much urgency and respect as if it were a physical health emergency, travel safely in suitable transport to where the right help is available” |
| --- |
| No | Action | Timescale | Led By | Outcomes |
| DEVELOPING SINGLE POINT OF ACCESS: Public Facing (111 & 999) |
| 14 | Call handling / dispatch Surrey Police introduce a better vulnerability assessment when incidents/calls are received. This will be developed jointly with SABP Pilot SABP staff within police control room environment for immediate access to SABP systems to ensure the best deployment decisions are made Pilot for then using that joint-call handling function to deploy the most appropriate asset – police, SABP staff etc., dependent on need | by Sept 14 | Police / SABP | This would be a really symbolic approach and should assist in preventing individuals entering the system when they’re in crisis. |
| DEVELOPING SINGLE POINT OF ACCESS: Specialist MH Facing (SABP) |
| 15 | Establish a 24 hour mental health crisis universal single point of access: | April 2015 | SABP | Culture change that will ensure appropriate response based on professional assessment and triage |
| 16 | Agree a SPA model that is universal and integrated with Voluntary sector and 111/999 services | November 2014 | Delivery Group | Mental health will receive the same response as people with a physical health crisis would rceive |
| 17 | SABP to develop partnership with voluntary sector on the running of the crisis line that will be an integrated part of the SPA. | Dec 14 – Mar 15. | SABP | Voluntary sector involved in delivery crisis line within a whole systems response offering increased capacity, wider access to the public, less stigma and value for money. |
| 18 | Closer working arrangements between SABP, 111 and 999 for mental health crisis and prevention agreed | November 2014 | SABP | Efficiencies to all agencies consistent with a seamless service response. Mental Health receiving parity of esteem to physical health |
| 19 | Co-location with 111 / 999 | April 2015 | 111/partners | To support single point of access pathway |
| 20 | Identify and procure supporting IT and telephony systems | Dec 14 – Mar 15 | SABP | IT and telephony will facilitate call handling for the single point of access – these will facilitate quicker response; less duplications and hand-offs between services offering efficiencies, increased capacity and safer services |
| Crisis / Emergency Response |
| 21 | Enhanced HTT | 15/16 & 16/17 | SABP | More capacity for swift response/informing choice/home treatment especially OOH |
| 22 | Integrated working protocols with HTT/Substance Misuse/CAMHs/Criminal Justice teams/LD | Sept 14- Feb 15 | SABP/Public Health/CAMHS/Police | Better communication and interagency working between community mental health teams and others Least restrictive, most local and effective response to crises. |
| 22 a | MH & Substance misuse commissioners to ensure that liaison and diversion services refer individuals with a co-existing MH and SM problems into appropriate services which can address their needs. Actions: MH workforce development; drug and alcohol awareness screening and referral MH and Susbstance Misuse liason; Care coordination across MH/SM SM advice, support consultation available to MH | Development and implementation Q3 and Q4 14/15 Delivery as core practice from Q1 2015/16 | Public Health | The needs of services users with co-existing mental health and substance misuse needs are better addressed in the development of services |
| 23 | Ensure there are adequate liaison psychiatry services in Emergency Departments | 15/16 (waiting for definition of adequate liaison) | NHSE/RCP/CEM | Parity of urgent access standards for people experiencing MH Crises |
| 23a | Establish baseline for parity of urgent access standards for people experiencing MH Crises | 15/16 | NHSE/RCP/CEM |  |
| 24 | Review arrangements for out of hours AMHP provision | March 2015 | SCC/SABP | Reduction in delays experienced awaiting AMHP assessment |
| Young Persons- 25 |
| 25 | Identify two staffed ‘crisis places’ (136 suites?) in supported accommodation for adolescents requiring respite for a maximum of five days, for adolescents unable to return home following an emotional or mental health crisis. | April 2015 | CAMHS- Diane McCormack / Karina Ajaya | To improve the response to the emotional wellbeing and mental health needs of adolescents. |
| 25a | Development of a co-commissioning approach with NHS England to ensure local pathway and availability and access to in-patient beds when required | April 2015 | CAMHS- Diane McCormack / Karina Ajaya | To ensure a local accessible pathway |

| Quality of treatment and care when in crisis:- “I am treated with respect and care and receive support and treatment, without unnecessary assessments, from people who have the right skills in a setting that suits my needs. Staff check any relevant information about me and, as far as possible, they follow my wishes and any plan I have voluntarily agreed to. If I have to be held physically this is done safely, supportively and lawfully, by people who understand I am ill and know what they are doing. Those closest to me are informed about my whereabouts and timely arrangements are made to look after any people or animals that depend on me.” |
| --- |
| No | Action | Timescale | Led By | Outcomes |
| 26 | An integrated information spine for crisis care plan information to be available across agencies | November 2015 | ECP Group | Prevent people escalating further in their crisis; ensure individuals preferences and their contingencies in their care plan are known and acted on where possible. This could avoid conveyance to A&E when not appropriate and reduce use of section 136, EDT and AMHPs. |
| 27 | Urgent review/relaunch of Missing Persons/Absconders and Welfare Check protocols as current protocols place requirement on staff and police that are not being complied with. | September / October 2014 | Police/SABP | Protect those who are going missing. |
| 28 | Review Repeat Venues for absconding – joint assessment of top 3 venues to agree action plan to reduce absconders etc. | July – Aug 2014 | SABP (police can assist) | Prevent future absconding |
| 28a- NEW March 15 | MISPER Compliance- benchmark & trajectory agreed | 30th April 2015 | SABP & Police | Prevent future absconding |
| 29 | Police Arrests/Custody Better handovers from police to place of safety, detailing circumstances 3hr assessment time limit (our protocols currently say 4hrs) Develop information sharing with police when S136 assessment beds are full (ie surge times), so that custody suites/police can be ‘made ready’ | Sept 14 | Police SABP SABP |  |
| 30 | Restraint, Searching, Police attendance at MH wards etc. Review and development of current SABP search policy, SABP/Police to jointly agree each agencies roles/requirements Ensure agreement is reached and policy is clear on when Police will be called (ie crime committed) rather than heavy police involvement for a crisis that could be managed by staff Positive Police action when called to criminal matters | Sept 14 | SABP/Police | To have a joint policy that reinforces this is a joint resolution |
| 31 | Advocate access | April 2015 | SCC | Improving access to advocacy for people in MH crises. Potential to explore s135/136 access to advocacy as a specific action. |
| 32 | Accessible info on services and standards | Nov 15 | SCC/CCG |  |
| 33 | Transitions standards |  |  |  |
| 34 | Environment standards in A&E Audit of MH assessment rooms in A&E | During 2014 | CEM through the PLAN accreditation network | Service Users experience a safe and improved environment and staff safety is improved |
| 35 | Review agencies protocols on restraints to ensure in line with national guidance | Nov 14 | Delivery Group | Part of a wider programme to reduce the use of physical restraint in mental health |
| 36 | Develop resources to support safeguarding boards, specific to the circumstances and needs of, and responses to, people experiencing mental health crisis | Dec 2014 | SCC/ADASS | Ensure effective planning and monitoring and review of local safeguarding arrangements. |

| Recovery and staying well / preventing future crises:- “I am given information, and referrals about services that will support my recovery. I am supported to reflect on the crisis and develop a plan for how I wish to be treated if I experience a crisis in the future. I am offered an opportunity to feedback to services my views on my crisis experience.” |
| --- |
| No | Action | Timescale | Led By | Outcomes |
| 37 | Repeat presentation prevention planning | 15/16 | SABP Primary care |  |
| 38 | Standards set for the use of care plans and contingency planning | 15/16 | SABP | Service users jointly produce contingency plans in case of relapse or crisis |
| 39 | To the attention of Health and Social Care services vulnerable people identified in the course of the day to day policing | Ongoing | Police | Prevention of crisis due to relapse in poor MH experienced by a vulnerable person |
| 40 | MH & Substance misuse commissioners to ensure that liaison and diversion services refer individuals with a co-existing MH and SM problems into appropriate services which can address their needs. Actions: MH workforce development; drug and alcohol awareness screening and referral MH and Susbstance Misuse liaison; Care coordination across MH/SM SM advice, support consultation available to MH | Development and implementation Q3 and Q4 14/15 Delivery as core practice from Q1 2015/16 | Public Health | The needs of services users with co-existing mental health and substance misuse needs are better addressed in the development of services |

# Text boxes

Surrey mental health crisis care concordat:

our joint declaration

‘We commit to work together in Surrey to improve the system of care and support so all people and their families in crisis because of a mental health condition are kept safe and helped to find the support they need – whatever the circumstances and time of day or night in which they first need help – and from which ever service they turn to first.

We will work together to prevent crises happening whenever possible through prevention and early intervention. We will make sure we meet the needs of vulnerable people in urgent situations. We will strive to make sure that all relevant public services offer high quality support to someone who appears to have a mental health problem to help move towards recovery.

Jointly, we hold ourselves accountable to enable this commitment to be delivered across Surrey’.