## Slide 1: Somerset’s Crisis Care Concordat Update
Deborah Howard - Head of Mental Health Services, Somerset CCG & Somerset CC
12 November 2015

## Slide 2
Summary
Background
Where we have got to
What’s going well
Not so well
Next steps

## Slide 3
Background
Crisis Care Concordat Action Plan developed in February 2015
Time of staff changes (retirement/recruitment) & absence at CCG
Pressures/competing demands on all agencies
Timescales within the plan – needed to revisit and re-set. This has been a recent realisation!

## Slide 4
Where we have got to 1/4
Declaration now signed by all partners
Quarterly multi-agency meeting chaired by Joint Head of Mental Health Services
Very well attended by partners, membership broadly mirrors the S.135/136 monitoring group which is helpful
Setting the tone/intentions for the each meeting - reminding us all of our purpose before we start

## Slide 5
Where we have got to 2/4
Regular update on Action Plan to Somerset SAB & LSCB
Starting to do the same for Suicide Prevention Advisory Group
Developed proposal & business case for 24/7 CRHTT - moving forward £ investment. SPFT at recruitment stage.
Multi-agency groups meeting to review/learn/share - based on cases/what’s happened. Reviewing incidents & complaints, service developments & care pathways. Regular case review group for multiple/repeated section 136 detainees

## Slide 6
Where we have got to 3/4
Agreement that education & training should be multi-agency
V. helpful meetings with A & S Constabulary -control room based Triage solution business case
Conveyance/transport being revisited. AMHPs booking private transport, due to concern re. waits, therefore difficult for provider to understand level of need etc.
Passion and commitment in Group is evident + good relationships at a local level inc. Police and Wards

## Slide 7
Where we have got to 4/4
Updated and improved place of safety environment at Rowan Ward, Yeovil
S.135/136 Policy review group – near to completion of review

## Slide 8
Not so well
Crisis/Recovery House or Sanctuary provision – large rural area, need to think through the best model for our population and unclear re. funding for this? VSO looking into needs too and reporting back. Keen to learn from other areas!
Information sharing agreements across agencies – concerns re. duplication of work across a range of meetings, often involving the same people – working smart across our system
TIME (huge issue) and sharing lead roles to take forward actions – but improving!

## Slide 9
Next Steps
Shared learning – across other areas, not duplicating effort esp. re. Crisis/Recovery houses or sanctuaries
Re-look at needs in respect of POS – 2017 likelihood Adults will have to go to health based POS.
Sub groups need to be set up to take forward actions so we can maintain growing momentum and take forward the actions within the newly set timescales