## Open Actions
| RAG Status | Complete | Ongoing / On track |  | Not achieved / Not on track for completion
OPEN ACTIONS
| Requirement | Action | Responsible Lead | Date for completion | Update | RAG status
1 | To develop a system to monitor progress on workstreams developed to support the Crisis Care Concordat Steering Group focus of reduction of inappropriate S136. | To establish a monthly meeting | Working group chairs | 9th October 2015 | Working group established, monthly meetings arranged.
WORKSTREAMS UPDATE
2 | Mental Health Triage Service
| To establish a Mental Health Triage Service provided by KMPT staff within Police and Ambulance Control Rooms, Out of Hours to provide access to information and to assist first responders with support to patients presenting in a mental health crisis. | OUT OF HOURS
2.1 |  | To review IT requirements in Ambulance HQ | KMPT / SECAmb | 2016-02-01 | IT issues identified with compatability of use in SECAmb HQ
2.2 |  | Service commencement out of Ambulance Control Room | KMPT / SECAmb | 31st October 2015 | Delays experienced relating to governance processes in place for service delivery in Ambulance Control Room. Governance arrangements to be reviewed internally and agreement sought in February 2016
2.3 |  | To assess service outcomes at 3 months | All attendees | 31st January 2016 | To be established once service commences
IN HOURS
2.4 |  | To assess service outcomes at 3 months | Criminal Justice Liaison and Diversion Service (CJLDS) | 31st January 2016 | To be undertaken following implementation of the service. Meeting arranged for 27th January to assess outcomes
3 | Frequent Attenders Working Group
3.1 | To establish a Frequent Attenders Working Group in order to individual care plans and preventative measures are in place, following a crisis, to prevent further occurrences share information and action taken to de-escalate | Establish professional links across the system of co-ordinators employed within separate organisations to provide co-ordination and involvement of the patients GP and other professionals | All attendees at frequent attenders working group | January 2016 | To be established once signposting co-ordinator is in post
3.2 |  | Appoint a dedicated co-ordinator (Clinical) to ensure that care plans are in place, patients are followed up and appropriately signposted or referred to existing health and social care services, develop bespoke packages of care as appropriate and help identify gaps in service provision as investment priorities | Medway CCG | January 2016 | Post approved for Medway CCG by SRG / Executive Board. JD developed, Host provider identified, service due to start in January 2016
Shared Care Database
4.1 | Multi Agency shared database for crisis intervention | To agree a protocol that defines the information required for uploading, governance arrangements, lead provider for managing the databse and responisbilities of those uploading to the system | All orgainsations | February 2015 | In draft form, to be shared and discussed at the next meeting in December
4.2 |  | To develop a database for sharing information across all partners electronically (Build on IBIS within the Ambulance trust) through Virtual Private Network at appropriate information governance levels of access. To assist with Care Plans and Assessment and access to data in time of Crisis known to all partners | All orgainsations | February 2015 | Ongoing meetings to establish service development and implementation requirements
5 | Clinical Interface Working Group
5.1 | Clinical Interface Group | To develop a standard operating procedure to ensure clear outlines on data sharing is defined | Medway CCG / KMPT / SECAmb / Kent Police / Medway Council / Meddoc/ NHS 111 | December 2015 | In development
5.2 |  | To establish a cohort of appropriate patients for review in the interim period prior to appointment of the signposting co-ordinator | Medway CCG / KMPT / SECAmb / Kent Police / Medway Council / Meddoc/ NHS 111 | December 2015 | Personality Disorder attendees identified as the intial cohort of the review. Currently obtaining consent from each service user
5.3 |  | To undertake a clinical review of those identified as a priority and enagage all partners to enable a shared review of individual needs and care planning requirements. | Medway CCG / KMPT / SECAmb / Kent Police / Medway Council / Meddoc/ NHS 111 | Ongoing | Personality Disorder patients have been identified as the initial priority and a template is in development (17 patients were identified, 8 reviewed at the meeting) multi agency care plans are being initiated. This service will be reviewing
6 | Single Point of Access
6.1 | Single Point of Access | To implement a Single Point of Access | KMPT | February 2016 | Clinical facing service on track for implementation in February 2016. Screening tool in development
6.2 |  | Review role / use of Single Point of Access arrangements for accessing AMHP requests | KMPT | 2016-02-01 | Review underway to align AMHP services with the SPA. Expected to be completed by February 2016
7 | Operational Policy Development
7.1 | Operational Policy Development | To work across all partners to agree a Standard Operating Procedure across Kent (SOP) | All services | April 2016 | First draft shared at T&F Group 9 October 2015. Final version to be ready for adoption in contracts April 2016.
7.2 |  | To establish a small operational group, map a draft pathway that includes IT solutions (Information Sharing and Governance and use of IT Systems e.g. IBIS) | All services | April 2016 | Initial scoping meeting taken place, future meetings to be arranged
8 | S136 Project
8.1 | Canterbury Christchurch University Section 136 project | The Police and other stakeholders are engaging with Canterbury Christchurch to agree research process and outcomes | Kent Police | April 2016 | Researcher appointed, awaiting submission of the vetting form to enable commencement.
8.2 |  | Consider support from AMHP trainees | Kent Police / KMPT | April 2016 | On hold following researcher appointment. To access AMHP support as required.
9 | SUPPORTING ACTIONS
9.1 | Multi agency staff to be aware of local mental health and substance misuse services for children and adults and know how to engage these services locally. | PCLDS work closely with local substance misuse services. | KMPT/ Substance & Alcohol Misuse Services | 2016-04-01 | Joint access to Rio established
9.2 |  | KMPT have a dual diagnosis steering group, strategy needs to be communicated internally. . |  |  | Dual Diagnosis protocol established for adult services. Prison in reach work has commenced with prison discharge pathways being reviewed.
9.3 | Revaluate protocols around dual diagnosis to ensure streamlined access into substance misuse service occurs. | To review current arrangements for Dual Diagnosis for children services | SPFT/ Substance and Alcohol Misuse Services | 2016-04-01 | Substance misuse services for the CAMHS age group are provided by: KCA Addiction in Kent and Open Road in Medway. CAMHS in Kent & Medway provide a service to young people where there is substance misuse and a mental health problem.
9.4 | To review and develop training arrangements and assess the need for joint training modules across services | To assess current training arrangements and assess the need for joint training modules across services | All subgroup partners to monitor | March 2016 | Training is provided to student officers, PCSOs and custody staff. Police led 1/2 day training session has been established between KMPT/Police CAMHS provide training to A&E staff NHS Security staff-gap in their training regarding identification/approach to people with mental health conditions.
9.5 |  |  |  | 2016-03-01 | Proposal to Steering Group to establish a training schedule of all providers MH training provided to staff.
9.6 |  | Develop multi agency training programmes to underpin the Standard Operating Procedures and Operational Policy |  | March 2016 | KMPT/Police have worked in partnership to produce a series of videos around regarding identification/approach to people with mental health conditions.
9.7 | Review suitability and availability of Places of Safety. | To refurbish 136 suites across Kent to bring in line with national standards | KMPT | December 2015 | Dartford suite refurbished in August 2015, functioning suite with snagging requirements to be reviewed and updated. Canterbury suites under refurbishment in October 2015, expected to be reopened in January 2016
9.8 |  | To review refurbished 136 suites to assess suitability | CCGs | January 2016 | NK CCG visits to Maidstone and Dartford suites. Visit undertaken to St Martin's, Canterbury prior to refurbishment works undertaken, revisits required following completion of the works.
9.9 |  | Consideration of dedicated suite for CAMHS | SPFT/CCGS/NHSE | Ongoing | Short term Place of Safety for children opened in Dartford, longer term situation may involve increasing capacity within current 136 suites. Child 136 detentions monitored by regular multi-agency meetings. One third of Child & Adolescent section 136 detentions access the Place of Safety in Dartford, the remaining young people have to be detained in A & E departments due to the lack of capacity for this age group across Kent & Medway.
9.1 | Police Officers should not have to consider using police custody as a place of safety for children. And if a police station is used police cells will only be utilised if there are exceptional circumstances. | It is an aspiration of the group that this is reported as a Never Event. | KMPT/SPFT | December 2015 | The framework for Never Events is nationally determined and this is not included within the criteria. This is an aspiration of the group however; it remains that if custody can do something that KMPT can’t it would still be the most appropriate place for the patient. This will continued to be monitored via the regional 136 monitoring group meeting.
9.11 |  | To define protocol if more than one child is detained at any one time. | KMPT/SPFT | December 2015 | There is an identified gap that if 1 child is already being assessed in the identified place of safety there wouldn’t be another option. Stephanie Clarke (KMPT) meets with Bob Lomas (CAMHS-Sussex Partnership) at an operational level and to develop solutions if the child place of safety is already occupied.
9.12 |  | Work with Local Authorities to manage transition and Individual Education and Health Plans against the Local Offer and Children and Families Act. | LA / KMPT / SPFT | TBC
9.13 | To identify the need for a safe place of care for people who are too intoxicated tor under the influence to undetake a mental health assessment | Investigate the need for a ‘safe place’ for care / containment and subsequent mental health assessment for people who are too intoxicated to be assessed / interviewed. | Acute Services/KMPT | Ongoing | If a patient is so intoxicated then A&E is currently the only viable option where their care can be provided for.
9.14 |  | To ensure solutions are included within emerging ‘Urgent Care’ Models being commissioned by CCGs |  | Ongoing | Urgent Care Models currently on hold due to instruction from NHSE
9.15 |  | Clinical physician from acute services to be invited to join group to develop protocols for intoxicated patients. |  | Ongoing
9.16 | Fast-track process that either provides an assessment or arranges transfer to a health based place of safety for individuals whenever a police cell is used. | To identify escalation processes for adults to ensure time in custody is limited | KP/KMPT/SPFT | On going | Escalation processes exist to ensure that dwell time in custody is limited. Adult patients (in cells) are prioritised for assessment.
9.17 |  | To identify and develop the fast track process for children |  |  | A child & adolescent patient on section 136 in a police cell is prioritised for assessment by CAMHS or transferred to the Dartford Place of Safety when it is available.
9.18 | To define timescales for response from health and social care, where police cells are used as a place of safety | To agree local timescales for response from health and social care where police cells are used as a place of safety | KMPT/KCC & Medway Council | 2016-02-01 | KMPT target to conclude assessment within 3 hours, an escalation policy is in place
9.19 |  | To review local response times following KMPT's CRHTT review of home treatment and prevention from crisis intervention | KMPT | 2016-02-01 | KMPT are currently reviewing their Crisis Home Resolution Treatment Teams to separate home treatment /prevention from crisis intervention.
9.2 | Develop the Psychiatric Liaison service to consider an all age approach. Current gaps including hours required within existing service provision to best meet patient need | To scope current service provision for adults in consideration of an all age approach to Liaison Psychiatry | CCGs/KMPT/SPFT | April 2016 | An all age LPS service is in development, following allocation of winter monies.
9.21 |  | To scope current service provision for CAMHS in consideration of an all age approach to Liaison Psychiatry | CCGs/KMPT/SPFT | April 2016 | November 2015 SPFT CAMHS have submitted a proposal for funds from the winter pressures funding to increase the availability of specialist CAMHS liaison psychiatry/crisis response. The proposal is for a 7 day 2 shift model 08.00 – 14.00; 14.00-0000hrs. 1 nurse per shift per A & E department and include working with emergency presentations, as well as some ‘in reach’ to paediatric words, training for acute staff and potentially some joint working with AMHS Liaison Psychiatry Service colleagues for the 16-18 yrs. age range.
9.22 | Review interface between daytime AMHP and Emergency Duty Team (EDT) to include Out of Ordinary Hours (OOH) assessments | To establish arrangements across Kent and Medway for interface between in and out of hours | AMHP / KMPT | 2016-02-01 | There is no separation between daytime and an OOH service in Kent. Agreement reached with Medway Council for KMPT to provide AMHP services in and out of hours. MOU currently in development and the protocol is being updated to reflect this provision of service.
9.23 | To evaluate a move to 3 hr waits for MHA assessments | Work towards acknowledgment and acceptance of initial MHA assessment for adult services within 3 hours | AMHP / KMPT / SPFT | 2016-04-01 | KMPT do not feel working towards a 3 hour wait for MHA assessments for adult services is deliverable or safe and requested rewording of the action point to read work towards acknowledgement and acceptance of initial assessment within 3 hours.
9.24 |  | Work towards a 3 hour wait for MHA assessments for children services |  |  | CAMHS are not at this time in a position to achieve this target They are looking to develop or implement actions to achieve the target
9.25 | Review multi-agency conveyance guidance for persons detained under Mental Health Act 1983 | Review the use of an appropriate alternative vehicle in the event of conveyance being required in a mental health emergency and only in exceptional circumstances should a police vehicle be used to transport a patient to a place of safety. Local implementation of the Association of Ambulance Chief Executives national S136 guidelines for transportation for people under Section 136 to include review use of SECAmb mental health pathway. | Kent Police / SECAmb / KMPT | Ongoing | Medisec are used to move patients, feedback is good across services. Further exploration is required to enhance use of Medisec and will be reviewed in line with the MHTS.
9.26 | To review/combine Section 135(1) and Section 135(2) policies | Policies to be reviewed/developed in light of the changes to the Mental Health Act Codes of Practice. | KMPT/KP/SPFT | TBC | Clarity to be established regarding responsibilities.

## Closed Actions
RAG Status | Complete | Ongoing / On track |  | Not achieved / Not on track for completion
CLOSED ACTIONS
Requirement | Action | Responsible Lead | Date for completion | Update | RAG status
To develop a system to monitor progress on workstreams developed to support the Crisis Care Concordat Steering Group focus of reduction of inappropriate S136. | To identify appropriate attendees |  |  | Attendees identified and engaged
WORKSTREAMS UPDATE
OUT OF HOURS
To establish a Mental Health Triage Service provided by KMPT staff within Police and Ambulance Control Rooms, Out of Hours to provide access to information and to assist first responders with support to patients presenting in a mental health crisis. | Disclosure and Barring Service (DBS) Process to be established for appointed staff |  |  | Vetting process established for 2x Band 4 staff. 1 B4 staff member withdrawn. Vetting not approved for Band 6 post however, post working out of Priority House.
| To review IT requirements in Police HQ | KMPT /Kent Police | July 2015 | IT requirements reviewed, system go live took place on 17th December for Kent Police HQ,
| To develop KPIs to monitor and evaluate the effectiveness of the service | All attendees | September 2015 | KPI screening tool developed and in place following commencement of the service
| Service commencement out of Police Control Room | KMPT / Kent Police | 2015-10-01 | Service commencement delayed due to DBS. Service commenced 17th December 2015
| To agree the use of funding allocated by NHSE | All attendees | October 2015 | Funding allocation confirmed by NHSE to be used to pilot the in hours service provision only.
| To establish a working group to monitor progress against service delivery | CCG Leads | July 2015 | Meetings arranged to monitor progress, virtual update facility also established
| To develop and agree a service delivery model | KMPT | October 2015 | Model options provided and updated against progression of discussions and requirements identified
| To agree funding arrangements across Kent and Medway | K&M CCGs | July 2015 | CCG funding identified across Kent and Medway
| To develop Job Descriptions and recruit to posts | KMPT | July 2015 | JD's developed and agreed, posts advertised and recruited to.
IN HOURS
| To develop KPIs to monitor and evaluate the effectiveness of the service | Criminal Justice Liaison and Diversion Service (CJLDS) | October 2015 | KPI screening tool in place following commencement of service
| Service Commencement | Criminal Justice Liaison and Diversion Service (CJLDS) | 30th November 2015 | Service commenced 30th November.
| To enhance the role of the Custody Liaison Officer to support a pilot service in hours (8am - 8pm) | Criminal Justice Liaison and Diversion Service (CJLDS) | October 2015 | Pilot site established as Ebbsfleet Poloce Station. Training delivered to staff. Police radio access and lone working process established
Provide a ‘System Wide’ integrated response to people at risk of or in Crisis through an Urgent Response ‘Task and Finish Group.- Workstreams established include Frequent Attenders Working Group, Multi Agency Shared Database for Crisis Intervention and Clinical Intrerface Group (updates outlined below) | To establish monthly meetings | KMPT | 2015-11-01 | Task and Finish Group established and meeting monthly
| To develop and agree a programme brief | All attendees | Sept 15 | Programme Brief approved by Steering Group
| To develop Terms of Reference | All Commissioning Leads | Completed through SRG Plans and submissions | Terms of Reference agreed
| To develop and agree a project plan | All attendees | Sept 15 | Project Plan in place with actions for delivery, lead names and timely deadlines. This is monitored each month by the members of the T&F Group
To establish a Frequent Attenders Working Group in order to individual care plans and preventative measures are in place, following a crisis, to prevent further occurrences share information and action taken to de-escalate | To identify and share information across all partners of those frequently using both physical and mental health services. | All attendees at frequent attenders working group | September 2015 | Systems reviewed, definition of frequent attender critieria agreed, cohort of frequent attenders determined
| To develop a multi agency repeat attender protocol | All attendees at frequent attenders working group | September 2015 | ToR developed which outline the process
| Identify those individuals most at risk of crisis across physical and mental health | All attendees at frequent attenders working group | September 2015 | Cohort of patients identified for initial review
Clinical Interface Group | To establish an ‘Interface Group’ of professionals who can jointly provide a multi-agency assessment of their needs within a ‘Safeguarding’ framework. | Medway CCG / KMPT / SECAmb / Kent Police / Medway Council / Meddoc/ NHS 111 /Turning Point | October 2015 | Attendees identified, clinical input established. Governance arrangements reviewed, all attendees have signed up to the information sharing agreement.
Mental Health / Social Care Signposting Resource | Develop cards and email signposting tool for Police Officers / Staff who have contact with the public | Kent Police | October 2015 | Cards developed and distributed to officers across Kent and Medway
SUPPORTING ACTIONS
Agree a suite of revised KPIs to monitor outcomes and impact | To develop a suite of KPI's to monitor progression and effectiveness | MH Concordat Steering Group | August 2015 | KPIs agreed at MH Concordat – August 2015
| To link KPIs into performance dashboards alongside System Resilience and NHSE reporting requirements |  |  | KPI's aligned to workstreams and reviewed at the monthly working group.
To identify the need for a safe place of care for people who are too intoxicated to undetake a mental health assessment | Drugs and Alcohol Team (DAAT) to be invited to attend the working group | Chair | November 2015 | DAAT invited to attend
Review multi-agency conveyance guidance for persons detained under Mental Health Act 1983 | To enhance the multi agency conveyance policy through work with Surrey and Sussex Police and SECAmb | Kent Police / SECAmb | Ongoing | Kent police have policy in place, however , now working with Surrey, Sussex Police to develop a single conveyance with SECAMB
Review links with British Transport Police to involve them in preventative measures to tackle the challenges of mental health and other suicidal behaviour | BTP represetative to be invited to attend Concordat working group | KP | 01.01.15 | BTP representative invited and attends monthly meeting
Ensure availability and contribution of the Service User in the development of local solutions to supporting people in crisis | Healthwatch to be invited to the Concordat working group | Working Group Chair | November 2015 | Healthwatch Medway and Healthwatch Kent informed of the meeting dates
| Mental Health Action Group County Chair to be invited to be represented at the Concordat working group. | Working Group Chair | September 2015 | Chair invited, meeting dates advised and attendance acknowledged.
Revaluate protocols around dual diagnosis to ensure streamlined access into substance misuse service occurs. | To review current arrangements for Dual Diagnosis for adult services | KMPT / Substance and Alcohol Misuse Services | 2016-01-01 | Protocol established and in place.
Fast-track process that either provides an assessment or arranges transfer to a health based place of safety for individuals whenever a police cell is used. | To agree local timescales for response from health and social care where police cells are used as a place of safety. | KMPT / Kent Police / KCC & Medway Council | November 2015 | KMPT target to conclude assessment within 3 hours, as above there is in place an escalation process. It was agreed that this action will be reworded to acknowledge and acceptance of initial assessment within 3 hrs.
There should be no circumstances under which mental health professionals will not carry out assessments because beds are unava | Clarity on the position in regards to AMHP responsibility in undertaking MHA assessments. | KMPT | 2015-10-01 | AMHP responsibility - Mental Health Act assessments are not decided on in terms of bed availability, as this would constitute a departure from statute. S140 is clear that it is the responsibility of the Doctor’s attending the assessment to find a suitable bed and not the AMHP. The bed situation, when difficult does impact on the Mental Health Act Assessment process which can become very protracted. These issues are taken to the Mental Health Act Good Practice Group in the Trust.

## Progress Updates
|  | 9th November 2015 |  | Wednesday 9th December 2015 |  | 12th January 2016 |  | 9th February 2016 |  | 10th March 2016 |  | 12th April 2016 |  | 10th May 2016 |  | 12th January
|  | Update | Evidence | Update | Evidence | Update | Evidence | Update | Evidence | Update | Evidence | Update | Evidence | Update | Evidence | Update | Update | Evidence
1 | Mental Health Triage Service | Progress timeline spreadsheet attached. Service for OOH delayed due to vetting procedures, expected commencement start date moved to December 2015 Service for Inhours on track to commence 30th November |  | In Hours service commenced on 30th November OOH Service commenced on 17th December. OOH Operational policy updated (Nov 15). Pathway established for MHTS and Force and Ambulance Control room. Screening Tool developed to measure benefits of the service | [12 empty] | Initial outcomes appear to demonstrate an effective service, with the night service running 3 days a week and receiving referrals from Patrols into the Force Control Room. As at 31st December, 2 weeks operational, the service ran a service for 6 nights, during this time 27 referrals were received. 12 (44.44%) were potential S136 assessments. Of these 12, 10 were diverted. (83%) In the first 4 weeks of the daytime service covering DGS they received 25 referrals; 20 of these referrals were in a patients home so a S136 not applicable of the remaining community referrals 1 avoided a S136. A review meeting to assess outcomes is taking place on 27th January
2 | Frequent Attenders Working Group | 12 month funded posts - post criteria agreed as a 121 co-ordinator post to work between key agencies and service users. JD written for the signposting co-ordinator post, advert drafted and circulated to the group for comment. Host provider identified as MCH, final discussions underway to agree on-costs. Advert due out by mid November expected in post by Jan 16.
3 | Multi Agency shared database for crisis intervention | Ongoing meetings to establish service development and implementation requirements
4 | Clinical Interface Group | Attendees identified, clinical input established. Governance arrangements reviewed, all attendees have signed up to the information sharing agreement. Personality Disorder patients have been identified as the initial priority and a template is in development (17 patients were identified, 8 reviewed at the meeting) multi agency care plans are being initiated
5 | Single Point of Access | Staff consultation started on 1st Nov for 30 days SPA will be staffed through rotational staffing from Community mental health and older peoples teams Clinical triage from end of Feb 16 for urgent and emergency referrals by phone and written referrals Clinical triage for routine referrals from June 16 by phone and written referrals Public facing number so anyone can ring or self-refer and will replace 836 number for Police. If appropriate for secondary mental health service will give an appointment slot over the phone There will be an electronic summary sent to GP once clinical triage taken place currently GPs only receive electronic discharge summary from inpatients Call handling system can identify caller area from landline, will monitor number of calls, rings to answer, etcNo answerphone, caller will be placed in a Q if all lines busy Will trial video triage in January 16 with a few GPs |  | Phase Description Phase 1 24/7 access point in the form of a telephone number, manned by non-qualified staff Completed 03.11.14: East Kent / West Kent 01/12/14: North Kent Phase 2 24/7 clinically facing Single Point of Access In progress Due to complete end of Q4 Phase 3 24/7 Clinically facing Single Point of Access accepting all referrals into KMPT inclusive of Routine referrals In Progress – Dependent on recruitment
6 | Operational Policy Development | KMPT and Kent Police have met to outline and scope the scale of the review. A meeting is taking place in December to continue with the review | [14 empty] | KMPT and Kent Police working together to align a draft SOP. The revised welfare check process needs to be included along with other policies that have been aligned. A flow chart is being developed for easy reference at the front of the policy. Engagement from other services SPFT, KCC, Medway Council & SECAmb is now required to agree the SOP. Draft development of the SOP is expected by February 2016
7 | Canterbury Christchurch University Section 136 project | discussions are ongoing with Canterbury Christchurch University to establish and assign a researcher. | [14 empty] | Researcher has been appointed but difficulty in obtaining vetting forms is delaying progression of the project. Alternative provisions are being considered and progression is being pursued to enable commencement of the project.
8 | Mental Health / Social Care Signposting Resource | The resource has launched internally for officers across Kent and Medway to signpost appropriate people to relevant services. 50,000 cards have been distributed with 200,000 additional cards ordered.
9 | Additional Kent wide projects | S136 activity review - 103 detentions under S136 during 2015/16 did not identify a K&M CCG as place of residence and instead have been aligned under the categories outside Kent, unknown or blank. KMPT are undertaking a review of these incidents to assess what impact out of area detentions may be having on suite capacity across K&M