## CCC Action Plan Mar 15
CC
Introduction
The Mental Health Crisis Care Concordat is a national agreement between services and agencies involved in the care and support of people in crisis. It sets out how organisations will work together better to make sure that people get the help they need when they are having a mental health crisis. All partners in Leeds signed up to the Yorkshire and Humber Regional Crisis Care Concordat Declaration in December 2014.
This crisis action plan is for the City of Leeds. It has been drawn up by Leeds CCG Mental Health and Urgent Care Commissioners* a workshop held in February 2015 attended by a wide range of stakeholders including local Acute, MH and Third Sector providers, Service Users, West Yorkshire Police, Health and Social Care Commissioners and Yorkshire Ambulance Service. This plan captures actions identified at this workshop as well as ongoing work that impacts on the quality of crisis care and the service user experience in Leeds.
Leeds is undertaking a transformation both of Urgent Care services and also embarking on a programme of Implementing the Leeds Mental Health Framework. Mental Health Urgent Care is one of the 4 Urgent Care Transformation projects and Improving Crisis Care is one of 4 prioritised programmes of the Leeds Mental Health Framework 2014-17. It has been agreed locally that Mental Health Urgent Care transformation will be delivered via the Framework Crisis Care Programme and CCGs are in the process of recruiting a project lead to implement the agreed actions and priorities of this programme. Progress will be reported into the Leeds Mental Health Partnership Board and the Leeds Strategic Urgent Care Board:
There is also a Leeds Suicide Prevention Group led by Public Health. The suicide prevention work is clearly relevant to the crisis concordat plan but the detail and planning is managed through this separate arrangement for both adults and children.
This plan is focused on those areas specific to the concordat but the actions may be part of wider plan delivery. In structuring this Action Plan we have used the 4 principles of the CCC (but not specifically used the headings of the CCC template plan) to ensure that we capture the local needs of our population. This is the first iteration with the ambition that it will evolve as the Framework programme develops over the next 2 years.
A separate plan has been drawn up by the Yorkshire Ambulance Service which can be viewed here:
We wish to hear comments and suggestions for improvements and areas of work we should concentrate on. Following stakeholder circulation, this plan with comments and changes received will be presented to our Mental Health Partnership Board and our Strategic Urgent Care Board by the end of March 2015 for ratification and agreement by all the stakeholders.
*there are 3 Leeds CCGs. Mental Health and Urgent Care Commissioning is done by Leeds North on behalf of the 3 Leeds CCCs.

## CCC Action Plan Oct 15
Introduction
1. Access to support before crisis
No. | Action | Timescale | Led by | Outcomes | RAG
1.1 | Leeds CCGs are undertaking a feasibility study for a Leeds front end/single point of access for all mental health services. In 2015 Leeds North CCG will consult with stakeholders and produce a feasibility study on the procurement of a single point of assessment for mental health services in Leeds. | Feasibility study to be produced by end of April 2015 to go out to consultation. | Leeds CCGs – Jane Williams | GPs and other referrers will be able to refer people into a comprehensive triage and initial assessment process. Sitting behind the assessment will be a number of options ranging from primary and secondary mental health services to social prescribing to peer support and skills training. Outcomes: • Service users can access the type of support they need and therefore avoid reaching crisis point, • Service users can rapidly access crisis services should this be the most appropriate intervention. • Pathways and criteria are clearly defined as are interfaces between services. Update October 2015 Early model principles produced and model consultation process began in July 2015 until October 2015. First phase exercise was to consult on principles across a wide stakeholder group. Service User /Lived Experience Group commissioned to specifically consults user groups and members across the city. Early consultation document produced. Project team consulted across wider stakeholder groups reaching over 300 people, including service users & carers groups, GP’s, primary and secondary care health providers & clinicians, adult social care and public health colleagues and third sector providers.
1.2 | Commissioning of targeted training and awareness around suicide risk (ASIST, Safe-Talk, MHFA) | Ongoing already commissioned. | Leeds City Council – Office of the Director of Public Health Catherine Ward | · Both the general public and frontline staff will be able to recognise and either signpost and or support people at risk of suicide. • The menu of targeted training will contribute towards identifying and reducing the risk of suicide in key high risk individuals in our communities as set out in the Leeds Suicide Audit.
1.3 | Development of Social Prescribing Pilots within Leeds CCGs. To widen the choice of support offered at primary care, each CCG will procure social prescribing pilot relevant to the needs of their population. | Leeds West pilot up and running since September 2014. Leeds North and Leeds West at planning and pre-procurement stage. | Leeds CCGs are each procuring a different model to meet the needs of their particular localities. | The social prescription approach is recognised as an effective means of meeting the wider needs of patients, providing the potential to address wider socio-economic determinants of health such as low income, low educational achievement, poor housing and community safety. It can expand treatment options, providing greater choice and control for patients, empowering people with the knowledge, skills and resources to promote their own and their family’s wellbeing. Adopting a proactive approach to health promotion is an effective mechanism to enable intervention at an early stage, supporting people to engage in healthy behaviours and reducing repeat attendance in primary care and secondary care. October 2015 Update: NHS Leeds West Clinical Commissioning Group has funded a partnership of voluntary organisations, led by the charity BARCA, to deliver a social prescribing service (known as the Patient Empowerment Project or PEP) in conjunction with the 37 GP surgeries in West Leeds. Better Leeds Communities, Leeds MIND and Touchstone are formal partners, but many more grass roots organisations and community groups are part of essential voluntary sector support and delivery in order to improve the wider health and wellbeing of patients. Leeds North CCG - The main social prescription service for Leeds North CCG is still in the procurement phase. Procurement is due to conclude at the end of November with the deployment phase starting in December. The North model is three small social prescribing pilots at the following practices St Lane, St Martins and Oakwood Lane. Leeds South and East CCG have commissioned Leeds Mind, HAMARA, Irish Health and Homes to provide a social prescribing service across GP practices via a single point of access to a wide range community groups and activity in an easy, accessible way which aims to reduce social isolation and improve health and wellbeing.
1.4 | Postvention Bereavement Service:It has been recognised that those bereaved by suicide are at increased risk of emotional and mental health problems and suicide themselves. Support for survivors of suicide has been identified as a preventative step. The Service will set up, develop, deliver, run and evaluate volunteer led drop in and peer support groups in Leeds. | Update October 2015: Service officially launched on 10th September 2015 and contract awarded to Leeds Mind as lead agency April 2015. | Leeds City Council – Office of the Director of Public Health | Suicide survivors will receive appropriate postvention support and as a result will have the opportunity to access services and receive early interventions such as bereavement counselling, peer support and family therapy The expected outcomes will include: • A specialist provision and support in Leeds for those bereaved by suicide • The ability to respond to the need for suicide survivors in the population identified in the Suicide Audit for Leeds 2008-10 as set out in the citywide Suicide Action Plan in relation to postvention work. • The delivery of a postvention Service for the population of Leeds. • The Service will identify the needs of suicide survivors and work toward developing the service to meet this need. • The raising of awareness and importance of Suicide Bereavement work. • The ability to be effective by building in a robust evaluation of the service from the onset of the contract.
1.5 | Leeds Mental Health Framework Programme Priority – Leeds model of community mental health services | TBC Currently in planning phase with project lead still to be assigned and project scoped. | Catherine Ward | Leeds has a fit for purpose model of community mental health service spanning NHS and third sector provision that can meet the diverse and complex needs of the population. Access criteria and information about services will be clearly described so that referrers and service users can navigate the Leeds model and reduce numbers of inappropriate referrals and reduce the length of time service users wait to access treatment. People are supported by a workforce with the right skill mix to meet their needs which will promote recovery and reduce the likelihood of relapse and mental health crisis. Joint work between Local Authority and CCGs to commission the model. October 2015 Update: Mental Health Programme Manager in post, Community Re-design Project manager in post from July 2015. Governance and support mechanism for programme of works established with Strategic Provider Partnership Board, Programme Board and Steering Group established. Scoping of current need across commissioned services in progress across third sector and health and social are providers in October, November and December. Work streams now in early development to begin to review consultation feedback, define need definitions, produce outcomes measures and analyse future data. Work beginning to define where New Models of Care end and referral to Single Point of Access begins. Work with GP’s has begun to support mental health developments within New models care projects for mental health wrap around care. Needs based pathways will begin to define complex needs and intervention across a wide group of providers.
1.6 | Integrated Health and Social Care teams Following a successful pilot project CCGs to recurrently commission 3 dementia specialist nurses from LYPFT to work with the integrated teams covering Leeds. | 2015-05-01 | Leeds CCGs Tim Sanders/LYPFT – Alison Gordon | To work alongside Integrated Health and Social care teams to support assessment and care planning where mental health needs are part of a complex presentation. Team are able to rapidly access specialist mental health team support and any existing health records to ensure problems are addressed quickly to prevent escalation into crisis. Update October 2015: Commissioning Intention to enhance from the existing 3 x Band 7s to add Band 6 capacity and, ideally psychology time.
1.7 | Leeds Maternity Pathway - Ante and post natal pathways and the integration with mental health services. | Maternity Needs Assessment Completed. One Workshop of two has taken place to pull together actions targeted at improving the pathway. | Leeds CCGs – Jane Mischenko | Mental health needs in mothers is recognised and support offered early from a workforce skilled to meet that need.
1.8 | Assertive Outreach Teams both LYPFT AOT and Touchstone Community Support Team (Also relevant to 4. Recovery and Staying Well) | Ongoing work – already commissioned by NHS and Local Authority | Leeds CCGs/LCC/Touchstone/LYPFT | Recognising the importance of AOT in the MH Pathway in keeping people engaged in services and ensuring that mental health deterioration is recognised and early intervention offered before crisis situation can develop.
1.9 | Local Authority Commissioned Drug and Alcohol Services:Ensure that the new service specification delivers integration with primary and secondary care MH services. | Contract Awarded and mobilisation period underway to begin 2015 | Leeds City Council – Chris Dickinson/Diane Powell | People with co-existing mental health and substance misuse problems (dual diagnosis) have been identified as a priority group within the specification of the new drug and alcohol treatment and recovery service. LCC awarded the contract in December 2014 to a consortium led by DISC including BARCA, LYPFT (LAU), St Anne’s Community Services, St Martins Health Care Services. Their mental health offer includes specialised dual diagnosis case management and psychological interventions, and is supported by specialist staff including a consultant psychiatrist and consultant psychologist. Training will be offered by the provider to key stakeholders in Leeds to support an integrated approach to achieving recovery outcomes in the city. October 2015 Update: Forward Leeds service operational 1st July.
1. 10 | Shared training between Police and LYPFT Crisis Service: Leeds District Police sergeant training to include MH case studies and input from LYPFT crisis team | Beginning March 2015 and then 6 monthly sessions. | West Yorkshire Police – NIK Adams LNCCG – Jeanette Lawson | Training taking place for 154 sergeants in Leeds over March/April. Training includes briefing on Mental Health Services, Risk Management Training & the use of the police national decision model. The training is then embedded through a workshop to apply learning to operational scenarios. LYPFT Crisis staff will co-facilitate the mental health sessions. October 2015 Update: The crisis and urgent care project lead at LNCCG will be developing a training programme in partnership with police. It is the intention that the training would be delivered by the nurses in police control room on a rolling programme. This will be built into their job specifications if/when the pilot is recurrently funded.
1.11 | Implement actions following the whole system review of Children and Young People emotional wellbeing and mental health services | Ongoing | Jane Mischenko _ Lead for Children and YP Commissioning for the CCGs Jane Williams – Lead for CCG Mental Health Commissionning | · Review produced 11 recommendations. • Mental Health Commissioners have included Children and Families as a priority project for Mental Health Framework for Leeds. A project leader will be shortly recruited to lead this work stream • Children’s and Mental Health Commissioners are working together to implement the Leeds review recommendations as well the Future in Mind CYP Strategy for England.
2. Urgent and Emergency access to Crisis Care
No. | Action | Timescale | Led by | Outcomes | RAG
2.1 | Police MH Resolution Practitioner - Pilot Project to locate a 1.8 band 6 WTE MH nurse within the Leeds District Police Control Room at peak times (twilight shift) across 7 days. The nurse would offer telephone triage if necessary to facilitate early resolution and prevent further escalation of presenting behaviours and possible detention in police custody. The nurse on duty would be the Single Point of Contact for officers when dealing with non-urgent mental health work. | 12 months pilot starting May 2015 | Partnership between West Yorkshire Police and Leeds and York Partnership FT.Named leads: Judith Barnes and Nik Adams | The pilot would allow targeted work to meet the mental health demand placed on the police. It would assist the police to have earlier detection of mental health needs, improved outcomes for service users, better manage risk and ensure early diversion to the most appropriate pathway for the individual. The outcomes of the pilot are to: • Facilitate timely and appropriate mental health referrals. • Ensure quicker resolution for response officers. • Reduce deployment of response officers to mental health related non urgent calls. • Reduce Section 136 detentions. • Improve response times for mental health assessment within custody. • Increase understanding of mental health needs and services for officers • Improved risk management of persons perceived by police as low level risk. • Improve service user experience. • Early identification of deteriorating mental health, facilitation of referrals to appropriate pathways and repeat callers (see 3.6) • Sharing key actions from individual care plans to inform early decision making at incident. Update Oct 2015 - Pilot fully operational from July 2015. Mid-point review report completed pilot continuing with extra investment of an extra nurse for the remainder of the pilot. It has been logged as a Commissioning Intention for recurrent funding and will be taken though the Vanguard group for regional support
2.2 | Mental Health practitioners to be based within YAS/111 hub | Pilot Starting Autumn 2015 | YAS – Angela Harris. | YAS will be piloting mental health practitioners within the 999 hub for West Yorkshire to reduce the need for YAS staff to attend mental health calls or for those calls that have required YAS crews on scene the requirement for conveyance to hospital is reduced.
2.3 | LYPFT Crisis Assessment Service (CAS) Street Triage Pilot and Review:Non recurrent system resilience funding has been given to extend the Leeds Street Triage pilot from 10 hours to 24 hours. The pathway has also been opened up to Yorkshire Ambulance Service Recurrent funding secured for next financial year. | Pilot extension to run from December 1st 2014 until May 2015. Review completed during this timescale. | LYPFT CAS – Judith Barnes | The original pilot ran from Nov 2013 for 1 year and has already evidenced the following outcomes:- Reduced the number of S136 applied by approx. 30%. - Reduced the occurrence of service users being placed (under S136 MHA) in police custody - Increase understanding of mental health needs and services for officers - Improved service user experience. The pilot extension will allow the CAS and Police to review the impact of Street Triage and inform recommendations on the best future model for Leeds. Has been up and running 24 hours from December 1st. Early findings show that whilst there has been more S136 referrals in January compared to December there is still a step change down in terms of numbers from December 2014 when then the augmented service began. This is a 15.6% reduction in S136 referrals from when the service was 10 hours to when it went 24 hours which is in line with the prediction. Following the initial review there is national recognition that as over 60% of Street Triage contacts occur in private dwellings that the service is renamed Mental Health Triage. Whilst the introduction of Mental Health Triage has reduced Section 136 and continues to do so, there is also evidence that there is a significant increase (53%) in mental health work which has previously been unmet need. The implication of this demand on current resources is yet to be understood. Update October 2015 Year 2 mid point review completed. Based on 18 months of data there is an estimated further reduction of Section 136 detentions in year 2 by 3-4%, the overall projected reduction in Section 136 detentions since the inception of MHCT being 32%. Future developments include: • Review of current staffing configuration, shift times and location of service. • Further promotion of service in YAS • Support of police training
2.4 | Implementation of the LYPFT Acute Care Pathway Review findings to meet the needs of people who require an alternative to admission and the skills/provisions LYPFT has to meet those needs. Focussing on partnerships that may compliment or be better placed to deliver some those services alongside the Trust. | Project commenced September 2014 and changes to the pathway Implemented between March and August 2015. | LYPFT - Guy Brookes John Holmes | Two main groups have been identified:Dementia/Complex Later Life and Acute Mental Health. Outcomes will include: • Acute alternatives to hospital admission pathway that meets the requirements of people with acute mental health needs and people with dementia / complex later life difficulties. • Reduced reliance on inpatient beds through the development of a Crisis Assessment Unit (CAU) • Service users will receive the right treatment at the right time by staff with the right skills to meet their needs. October 2015 Update: All objectives from the Acute MH review now in place. Dementia/Complex Later Life project has a lead clinician John Holmes and currently recruiting a project manager. The project manager will oversee a number of projects and work with commissioners to implement the desired outcomes of: • support near to home • prevention of people being inappropriately admitted to hospital; • If admission is unavoidable, provide a clinically effective service to keep admission to a short a time as possible returning to home environment. This project is reporting into the LYPFT/CCG clinical service development group
2.5 | CCG have commissioned LYPFT to Develop a Crisis Assessment Unit for Leeds. The extra resource will build on the current crisis assessment service and increase their capacity to meet the needs of : • Service users who require more detailed assessment of need during crisis • S136 service users who are intoxicated and held in police custody • Service users who need an urgent assessment – more quickly than the current 4 hr standard. | CAU scaled implementation beginning January 2015 with 2 beds and eventually moving to an 8 bedded 72 hour extended assessment unit by Summer 2015 | LYPFT – Judith Barnes | The unit would improve the service users experience, reduce the need for admission to acute inpatient care, divert service users from urgent care and ensure parity of esteem for mental health service users receiving expert and detailed mental health assessment.The service will be predominantly aimed at: •Decreasing service users taken to police cells following detention using S136 MHA 1983 •Divert service users from A&E •Divert service users from admission to hospital It would not be possible to describe all possible situations when admission to the Crisis Assessment Unit would be appropriate however some key groups of service users who will benefit from the service are: •Service users presenting in an acute crisis following a significant event who need a brief period of support before their medium term needs can be accurately determined. It would be expected that this could be a community based service rather than inpatient admission. •Service users who require on-going care via Intensive Community Services who present out of hours and who cannot keep themselves safe. Currently service users would need to remain either in A&E or require admission to hospital. •Service users presenting at their GP requiring an emergency assessment of their mental health who do not have medical needs requiring treatment. •Service users who have contacted YAS requiring mental health assessment and whose physical health needs have been met by the paramedics. •Service users seen by police who have no medical needs but who require mental health assessment. Often this will have included an initial assessment via the newly commissioned MH Triage service. •Service users with “drug induced psychosis” requiring short term treatment in a controlled and safe environment. •Service users recalled using a community treatment order who will receive assessment in a supported environment. •Service users with a social related crisis precipitator who can be both treated and safety can be maintained whilst the situation which precipitated the crisis is resolved. •Service users detained by Police under S136 MHA who are intoxicated Update October 2015 Service operational from end of July 2015 with latest figures indicating 38 admissions since that time. Outcome measures for the service continuing to be developed.
2.6 | Dial House – Survivor led Crisis Service funded by health and local authority commissioners. Using NHS system resilience £ CCGs have commissioned an additional night capacity for 2 years at Dial House. | Service moves to 5 nights opening from December 2014. | Leeds CCGs – Debra Taylor –Tate and Jane Williams and Dial House - Fiona Venner | Service users are now able to access crisis support for 5 nights week at a survivor led crisis house in the community. Outcomes include: • Reduced use of urgent care (ED) • Reduced use of NHS mental health crisis services • Improved service user experience • Choice in crisis support in Leeds.
2.7 | Development of a Leeds Mental Health Urgent Care Steering Group to re-design and improve the Leeds MH Crisis Pathway. | First workshop 4th February to process map current pathway and future meetings TBC | Leeds CCGs Urgent Care Lead – Debra Taylor-Tate | A multi-agency workshop held to process map the current crisis pathway for service users entering ED.Projected Outcomes: • Establish a partnership approach to the transformation of MH crisis pathway. • Using real life recent examples of service users who have accessed MH services via ED to produce a process map. • Inform and focus the crisis care concordat work stream • To understand the importance of the diagnostic element of the pathway and how this should influence patient journey following presentation at ED. This should ensure that people receive right service at right time (parity) and seamless transfer between organisations in the pathway October 2015 Update: Crisis and Urgent Care Project Lead in post September 2015. Steering group have had initial meeting and work is ongoing.
2.8 | LYPFT Acute Liaison Psychiatric Service (ALPS) Evaluation | Evaluation to be complete and with commissioners by end of March 15. | LYPFT – Kim Bunton/Janet Wright | The evaluation will enable commissioners to analyse whether the service has achieved its original business case objectives:• Diversion of those presenting with MH/self-harm issues at ED away from acute admissions. • Fast access (within 3 hours) to a mental health assessment • Appropriate referral onto mental health service. • Improved service user experience. The evaluation report will be used to inform the Liaison service review in 2015. October 2015 Update: Evaluation completed and draft shared with Commissioners. Issues of capacity across shifts to deal with high volumes of referrals, capacity to train ED staff and capacity to provide joint “front door” assessments have been highlighted. Bid requested from LYPFT to pilot extra capacity within ALPS as part of the liaison in ED non recurrent money provide by NHSE.
2.9 | LYPFT/CCG Review of Liaison Services : In line with 2015 Planning Guidance and Better Access by 2020 targets, CCGs have funded a review of Liaison services across LYPFT. | TBC | LYPFT and CCGs | The review will scope out the work needed to ensure in Leeds we have a model of MH liaison that meets the needs and size of the population. October 2015 Update: LYPFT are in the process of recruiting project manager. LYPFT are working with Leeds University on models of Liaison Psychiatry. Review will include GAP analysis with CORE 24 model service specification. LYPFT are bidding for funds in partnership with LCH to pilot extra capacity within acute liaison with the aim of meeting CORE 24 outcomes – all age liaison psychiatry.
2. 10 | Expansion of the Older People’s MH Liaison Service:The Liaison Psychiatry Service for Older People undertakes specialist assessment and review of people aged 65 and over who present with mental health problems in General Hospital settings in Leeds | Additional nursing capacity in place January 2015 onwards. Funded NR from system resilience funds until April 15 when recurrent funding has been agreed from CCGs. | LYPFT OPS Liaison Team – John Holmes | Main benefit will be to improve the timeliness and access to appropriate assessment reducing the use of inpatient care and reducing lengths of stay for service users who are admitted to hospital. • Faster assessment of service users presenting at LTHT with regards to mental health needs • Parity of esteem for service users under 65 and over 65 years of age in terms of meeting physical health and mental health needs • Increase case finding of older patients with mental health problems and facilitate referral to appropriate services for diagnosis and treatment
2.11 | Information Sharing Protocols - West Yorkshire Police and LYPFT Crisis Service/LTHT ED | TBC |  | The purpose of this agreement is to establish a lawful, efficient, appropriate and confidential method of reciprocal data disclosure. This is primarily to ensure that a risk management plan can be accurately formulated for the service user to safeguard the individual, staff, and the public. This will be specifically aimed at the propensity to commit sexually related offences, harm oneself, violence towards others and violence towards property. Secondly to inform a reciprocal flow of data in the form of an information report, post risk assessment, by the Partner SPoC in the format required. This will ensure that officers and staff within West Yorkshire Police and the Trust Partner are jointly aware of the plan and able to assist the service user if the future need arose.
2.12 | Mental Health Crisis ID : To consider the creation of a simple identification card/bracelet that would enable police/ambulance/members of the public/others to easily identify people who may be in the midst of an acute mental health crisis. | To be confirmed when the MH framework crisis lead is in post. | To be confirmed when the MH framework crisis lead is in post. Together We Can will take a lead in developing this piece of work. | People in crisis will have an opportunity to “opt in “to this scheme. For those that have had negative experience in accessing mental health crisis support it should enable swift identification and access to the right service at the right time and reduce any confusion and negative experiences.
3. Quality of treatment and Care when in Crisis
No. | Action | Timescale | Led by | Outcomes | RAG
3.1 | Together We Can – Service User Crisis Report. Leeds MH Partnership Board service user representatives have produced a report of service user experience of crisis services. | Ongoing | Joe Alderdice and Together We Can | The report contains a number of recommendations that will be used to inform re-design of the Leeds MH Crisis pathway. The group will be included in the membership of the Leeds Urgent Care Working Group and this inclusion will ensure that any changes to the crisis pathway and planned service improvements are developed in collaboration with service users.
3.2 | Acute Liaison Psychiatry Service (ALPS):Providing self-harm service 24/7 to ED and medical wards and also mental health assessment to service users within ED. To facilitate prompt access to mental health intervention for those individuals who have an identified mental illness working closely with the acute care pathway to access in-patient psychiatric admission and intensive community services | Ongoing from February 2013 evaluation is due end March 2015. | LYPFT – Kim Bunton | The ALPs service aims to provide a mental health assessment within 3 hours of service users presenting at ED with mental health issues. Outcomes: • Service users will be provided with a thorough bio-psychosocial assessment and signposted to the most appropriate service to manage their current mental health and bio-psychosocial difficulties. • Improved ambulatory care pathway for service users with a mental health difficulty or following an episode of self-harm. • Closer and more consistent collaboration between LTHT and LYPFT to optimise efficiency in managing mental health and self-harm presentations in the ED.
3.3 | LTHT and LYPFT to review the escalation processes in place between LTHT Emergency Department and LYPFT crisis service. | Meeting 18th March to begin the process of agreeing an escalation process between LTHT/LYPFT and Police. | LTHT – Andy Davies LYPFT – Chris Hosker/Judith Barnes WYP – Nik Adams | Monthly meeting to formulate joint escalation policy. Each organisation will develop escalation flowchart & these will then brought together to form overarching plan. Once agreed disseminate to staff. Risk of Absconding management plan being developed with LTHT/WYP Update Oct 2015 – This work is ongoing with regular meetings between partners.
3.4 | Crisis Assessment Unit - extension of CAU capacity to meet the needs of intoxicated service users.Harm reduction workers located within the Crisis Assessment Service. Initial pilot phase funded via System resilience £ and recurrent costs agreed as a commissioning intention by Leeds CCGs. | Extended Section 136 suite will be operational in Summer 2015. Harm Reduction workers in post from January 2015. | LYPFT – Judith Barnes | Currently the S136 suite is unable to meet the needs of intoxicated or violent service users and so they are usually held in a police cell until a mental health assessment can be performed. Extension to the number of S136 beds and improved capacity of crisis service via CAU will mean that there is capacity for them to be brought to the S136 suite instead. This will improve service user experience. Update Oct 2015 – Extended 136 suite opening on 12th October 2015. Intoxication protocol developed. Interagency guidelines updated and circulated for comments Harm reduction workers will assertively follow up individuals identified via Mental Health Single Point of Access/ Crisis Assessment Service/ALPs to engage in harm reduction work to reduce re attendance to the Emergency Dept. or Crisis Assessment Service, improving outcomes for service users with co-morbid substance/alcohol use. Update Oct 2015 – Recurrent funding agreed. Mid point review report circulated for comment. Ongoing problems with data collection and demand out weighing capacity.
3.5 | Leeds Multi Agency S136 meeting - quarterly meetings to discuss issues relating to S136, street triage and any other interface issues between police/mental health and social care services. | Ongoing | LYPFT lead but attended by police, Leeds City Council, CCGs and other stakeholders. | The group is multi-purpose: •That the Trust has a robust clinical strategy to underpin operational and strategic planning. •Robust communication between all organisations. •Section 136/Street Triage monitoring figures are presented and discussed across all interested parties. •Delivery of Section 136 service development, improvement programmes and projects monitored and evaluated. •That the service has effective clinical governance systems and that quality issues are brought to the attention of the relevant organisations. •That the Section 136 service delivers on national and local performance standards •That Section 136 service risks are identified and managed and that strategic risks are escalated. To disseminate findings of street triage pilot. Update Oct 2015 – ongoing
3.6 | LYPFT Repeat Attenders Forum - a forum for LYPFT staff, representing key services, to review how the Trust responds to service users most frequently in contact with LYPFT ‘out of hours’ services. The ambition of the forum is to improve service user experience through meeting the above aims and to enable LYPFT staff to more robustly respond to the identified needs of this service user group. The focus of the group is to consider how the service is responding to the service user in question. | January 2014 and reporting into the Leeds Self Harm Partnership. | LYPFT – Crisis Assessment, Personality Disorder and Acute Psychiatric Liaison service leads. | The aims of this group are to ensure that: • Those service users most frequently in contact with LYPFT ‘out of hours’ services, i.e. (ALPS) & (CAS) are identified • Their contact with LYPFT services is briefly reviewed • Appropriate steps are then taken to seek to improve how LYPFT services can more effectively engage and / or respond to this service user group • If no LYPFT service is currently being provided that the rationale for this has been considered • That if a LYPFT service is currently being provided that the pattern of repeat attending & the response of those services involved has been considered It is anticipated that if the aims are achieved a reduction in the use of these services may result for some service users, through a more considered and ‘joined up’ response from LYPFT staff. October 2015 Update: LYPFT have been incentivised with a CQUIN To develop this work outside of MH services – eg to extend to police, third sector etc.
3.7 | Access to AMHPs – Adult Mental Health Professionals. Non recurrent system resilience £ has been allocated to LYPFT to train a number of nurses as AMHPs. | Training began December 2014 and qualified | LYPFT – Judith Barnes | The crisis team will be able to flex workforce to respond to the needs presenting. People will not have to wait for an AMHP mental health act assessment from the EDT. Update October 2015 - 2 Nurses completing their AMHP training December 2015 and March 2016. No more staff identified at the current time due to ongoing band 6 nurse gaps. Liaison Bid for extra nursing capacity within acute liaison will include nurses trained as AMHPs.
3.8 | Social Care input into crisis care and access to EDT? | To be developed in partnership with Leeds City Council. | TBC | To be developed in partnership with Leeds City Council. October 2015 Update: An EDT review workshop has been arranged for 9th November to agree pros and cons of proposed EDT models. Multi agency invited to attend and contribute.
3.9 | LYPFT implementation of Department of Health guidance on Prevention and Management of Violence and Aggression (PMVA) | Ongoing since June 2014 | LYPFT - Linda Rose | · Task and finish group with oversight of PMVA to draft restraint reduction action plan at the end of February 2015. • Board of directors have agreed sign up to the Restraint Reduction Network demonstrating organisation support for the mission and values. • Some LYPFT staff have been up skilled with de-escalation training. • Training needs analysis completed to ensure right staff are given the right level of training. • In process of agreeing restraint reduction models- service appropriate such as safe wards. Services are networking nationally to agree best practice models. • PMVA procedure is under review.
3. 10 | National Confidential Enquiry into Suicide and Harm: Qualitative review of suicides occurring with LYPFT services over last 2 years | Review begins early April and report due August 2015. | LYPFT – Anthony Deery | NCISH have agreed to undertake a qualitative review of the suicides that have occurred over a 24 month period from 1December 2012 to 31 December 2014. Such a review would draw on lessons learnt from similar reviews undertaken by NCISH and help identify ways in which LYPGY can improve the safe care and treatment for these patients October 2015 Update: The initial results of the review were presented at an event in Sept. From 12 SI reports, NCISH identified the following themes: • There need to be processes for staff to get to know patients better. - This was related to the issue of how busy teams are and the need to assess people but then having to move onto the next referral. • Ensure all historical and current behavioural aspects of patients risks are incorporated in the care plan. – This issue is the balance between forming a relationship and trying to gather as much information as possible. • Highlighting the crucial role of the physical environment in patient safety. – LYPFT has done a lot of work around this but how to manage patient’s home environment? • Improving co-ordination of care with patients with dual diagnosis. • Work more closely with family, carers and friends. –How to achieve this more effectively while recognising confidentiality. In addition, NCIH identified themes from national work which is relevant as well: • For men there is an increase in alcohol abuse and isolation. • The growth of Crisis teams and how they are performing • The need for early involvement with family and carers post discharge. • Identifying physical problems and their impact. LYPFT are forming a working group to action the recommendations and the first meeting is in November. There is commissioner representation on this group.
3.11 | LYPFT to undertake some work improving the recording of ethnicity of those accessing crisis services and then some analysis of outcomes across different ethnic groups. | TBC | LYPFT – Robert Mann | Ethnicity data is incomplete with many patients who access crisis services no ethnicity is recorded. The crisis service will undertake some work to improve this and also to explore raw data findings which suggests a larger number of people accessing crisis services via S136 are admitted to hospital.
4. Recovery and staying well / preventing future crisis
No. | Action | Timescale | Led by | Outcomes | RAG
4.1 | Wellness Recovery Action Planning (WRAP) – embedded in the new LYPFT Rehab and Recovery Service. Currently used by a number of staff but Recovery Centre lead will work to embed across the service. | New service from January 2015 and WRAP to be embedded as the service develops. | LYPFT Rehab and Recovery Lead – Recovery Centre (Stephen Dilks) | The WRAP approach helps guide the relationship between the therapist and the service user. It enables the service user to focus on their own unique story/recovery, what helps them stay well, their supportive networks etc and all this can be produced into a meaningful plan that supports them in crisis or difficult times. Key elements and outcomes include: • Wellness Toolbox • Daily Maintenance Plan • Identifying Triggers and an Action Plan • Identifying Early Warning Signs and an Action Plan • Identifying When Things Are Breaking Down and an Action Plan • Crisis Planning • Post Crisis Planning
4.2 | Dissemination of Crisis Cards Aimed at the general public to signpost to local Crisis Support services (broader than M H Services) | Ongoing | The Office of The Director of PH, LCC Catherine Ward | The wider population will have easily accessible information in relation to Crisis Support and self-refer to local services as identified through the suicide prevention action plan and meet the needs of at risk groups including debt services, employment and housing support. Frontline staff including the police will carry and use as a resource when working with at risk individuals, families and communities. Crisis cards will be available to the public eg. in one stop shops and local betting shops other than more traditional settings to help reduce stigma and barriers attached to Crisis Services. Update October 2015: Crisis card updated Autumn 2015 to include new services ( Alcohol and Drugs, Bereavement)
4.3 | Digital Patient Health Record: LYPFT are currently in the procurement process of a digital patient health record that comprises mobile and web software for use by patients and clinicians and be both Web and app based | Initial tender evaluation 5th March. Due to be piloted in the new Rehab and Recovery service at LYPFT. | MHealth Habitat (an LCH and LYPFT collaboration) – Victoria Betton | To engage service users in the co-creation of their healthcare in collaboration with their clinical team. Service users will have the ability to keep daily diary of mental health and interact with their care-co-ordinator as and when needed. Outcomes: • Increased patient self-management • Improved Self-Efficacy • Patient Engagement • Improved patient/clinician shared decision making
4.4 | Dial House Crisis Peer led Group Work: CCGs to extend funding to enable the group work to expand. | Ongoing | Dial House Manager - (Fiona Venner) | Peer led group work takes place at Dial House, with the following aims: • Reducing risk/preventing worse happening • Preventing the need for the use of Dial House and other crisis or emergency services • Reduced loneliness and isolation • Increased social inclusion through the provision of peer and social support.
4.5 | Peer Support Mapping Project | Summer 2015 – March 2017 | Steve Callaghan - LNCCG Kathy Engler - Leeds Mind | Leeds Mind has recently received Big Lottery funds to map peer support in the city and to develop a peer support network in the city. This is to enhance the current mental health peer support service in the city which is funded by Leeds Adult Social Care and the Leeds CCGs. The Big Lottery funding runs until March 2017 and links closely with the citywide re-design mental health community services – of which peer support is a core element.
Improved partnership working in Leeds locality
1 | Leeds Mental Health Partnership Board – Delivering the Mental Health Framework Priorities. | 2014-2017 | Leeds CCGs and city wide partners. | Leeds Mental Health Partnership Board (CCGs, Local Authority, Service Users and Carers and NHS and Third Sector Providers) have signed up to implement the Leeds Mental Health Framework. A series of 4 workshops have been held with all partners playing an active role in deciding priorities for Leeds. These include:
· Improving Crisis Care
· Transformation of Leeds Community Service Model
· Children and Families Mental Health
· Data
· Creation of an Information Hub
Work streams will be developed with Project Leads assigned and projects reporting back into both the Mental Health Partnership Board and Strategic Urgent Care Board.
2 | Suicide Prevention Strategic Group for Leeds | Current | Catherine Ward | Suicide action plan for Leeds in place, based on national strategy and Leeds Suicide Audit findings 2011
|  |  | Public Health (LCC) | Priorities include ;
- Primary care
- Bereavement (postvention)
- Community ( high risk groups)
- Media
- Data and Intelligence
Actions to date;
· Insight work completed and shared. Recommendations being acted upon new investment.
• SafeTalk and Asist training rolled out citywide with new investment
• Pilot Postvention Service to commence April 2015 from work identified from bereavement task group.
• Police and University key strategic partners
• Crisis cards for public produced and disseminated citywide
Update October 2015:
New Audit to be commenced Winter 2015 and led by Leeds City Council.
3 | Leeds Multi Agency S136 meeting - quarterly meetings to discuss issues relating to S136, street triage and any other interface issues between police/mental health and social care services. | Ongoing Quarterly Meeting | LYPFT lead but attended by police, Leeds City Council, CCGs and other stakeholders. | · Review street triage findings
· Discuss interface issues between MH, Social Care and Police
· Link with suicide prevention work streams
4 | Dual Diagnosis Network | Ongoing | Multi Agency Group facilitated by St Anne’s Karen Pearse | The Leeds Dual Diagnosis Project aims to promote evidence based best practice to ensure that the best care is delivered to service users with co-existing substance misuse and mental health needs in Leeds. The project aims to improve access to treatment and improve outcomes for people who experience dual diagnosis. It is a multi-agency network developed to ensure that services that come into contact with this client group are readily able to assess, engage and co-ordinate care effectively. The partnership includes professionals from a range of mental health, drug & alcohol, criminal justice and housing services who have a shared vision of collaborative and integrated treatment.
The Leeds Dual Diagnosis Project facilitates a variety of working groups and forums to achieve its aims including the DD Strategy Group, DD Working Group, DD Practitioner Network, ZIP (Service user and ex-service user group), Primary Care Working Group and the Northern and North West DD Group as well as contributing to and supporting the development of other relevant work streams in the city.
For more information visit www.dual-diagnosis.org.uk
5 | Mental Health Crisis & Urgent Care (concordat outcomes B&C) meeting | Every 6 weeks | CCG led | The MH Crisis & Urgent Care meeting will be responsible for influencing and supporting the deliveries outcomes B and C of the Crisis Care Concordat and developing solutions within the framework of National/Regional guidance.
|  |  | Jeanette Lawson | Other responsibilities include:
· Providing a collaborative partnership forum to gain mutual understanding of system flow
· Identifying service development and service improvement opportunities that will further enhance service user experience and improve system efficiencies
· Ensuring all members of the group are fully informed, and aware of current progress, risks and issues
· Sharing best practice and learning from both local and national experiences.
· Ensuring the service user is at the centre of our decision making.
· Enabling successful collaboration, communication, and partnership working across clinical groups, service providers and agencies.
· Identifying blockages in and risks to maintain effective service delivery and ensuring a solution focused approach.
6 | Frequent attenders at ED work steams | Quarterly | Jeanette Lawson - LNCCG | Coordination meeting of the number of frequent attendee schemes across Leeds looking at the management of frequent service users to ensure the schemes complement each other, reduce duplication and, ensure learning is shared
BARCA
LYPFT
The Mental Health Crisis Care Concordat is a national agreement between services and agencies involved in the care and support of people in crisis. It sets out how organisations will work together better to make sure that people get the help they need when they are having a mental health crisis. All partners in Leeds signed up to the Yorkshire and Humber Regional Crisis Care Concordat Declaration in December 2014.
This crisis action plan is for the City of Leeds. It has been drawn up by Leeds CCG Mental Health and Urgent Care Commissioners* at a workshop held in February 2015 attended by a wide range of stakeholders including local Acute, MH and Third Sector providers, Service Users, West Yorkshire Police, Health and Social Care Commissioners and Yorkshire Ambulance Service. This plan captures actions identified at this workshop as well as ongoing work that impacts on the quality of crisis care and the service user experience in Leeds.
Leeds is undertaking a transformation of Urgent Care services and also embarking on a programme of Implementing the Leeds Mental Health Framework. Mental Health Urgent Care is one of the 4 Urgent Care Transformation projects and Improving Crisis Care is one of 4 prioritised programmes of the Leeds Mental Health Framework 2014-17. It has been agreed locally that Mental Health Urgent Care transformation will be delivered via the Framework Crisis and Urgent Care Programme. Progress will be reported into the Leeds Joint Health and Wellbeing Board via the Leeds Mental Health Framework Programme Board and the Leeds System Resilience Group.
There is also a Leeds Suicide Prevention Group led by Public Health. The suicide prevention work is clearly relevant to the crisis concordat plan but the detail and planning is managed through this separate arrangement for both adults and children.
This plan is focused on those areas specific to the concordat but the actions may be part of wider plan delivery. In structuring this Action Plan we have used the 4 principles of the CCC (but not specifically used the headings of the CCC template plan) to ensure that we capture the local needs of our population. This is the first iteration with the ambition that it will evolve as the Framework programme develops over the next 2 years.
A separate plan has been drawn up by the Yorkshire Ambulance Service which can be viewed here:
This October update will be circulated to members of the Mental Health Crisis and Urgent Care steering group and formally presented to the Mental Health Framework Partnership Board and the System Resilience Group at their November meetings.
*there are 3 Leeds CCGs. Mental Health and Urgent Care Commissioning is done by Leeds North on behalf of the 3 Leeds CCCs.

## Priorities 16 -17
|  | Crisis Care Concordat Action Plan |  | Update June 17
Priorities 2016/17
Need | Action | Time scale | Led by | Outcomes | Nov 16 Update | June 17 Update | Lead Group
Children and Young People | To implement the actions outlined in the Local Transformation Plan (2015) which includes crisis as a priority. To ensure the CYP crisis pathway interfaces appropriately with adult services where necessary. To develop an enhanced liaison psychiatry pathway (all age Core 24) that meets the needs of 16 years and over. |  | Ruth Gordon Programme Manager for Children and Maternity Services, Leeds CCGs. Kim Bunton Clinical Service Manager Liaison Psychiatry, LYPFT. | To ensure current service provision adequately meets the needs of children and young people at the time of emerging and acute mental health crisis. To develop a robust crisis pathway for CYP within Leeds. | Workshop complete workstreams developing for Autistic Spectrum Disorder Safe haven response linking to Leeds Crisis café. Core 24 funding pilot in implementation phase | Core 24 funding pilot in implementation phase Children and Young peoples workstream established | B & C Transitions workstream of Future in Mind LYPFT perfromance management CYP crisis workstream meeting
Alternative Safe Spaces To develop a safe place that will be used as an alternative to the ED (Emergency Department) for people not requiring any physical health interventions. | To develop a ‘Safe Haven’ model for the city ensuring this is aligned to the WYUEC (West Yorkshire Urgent & Emergency Care) Vanguard project group. To secure funding via WYUEC (West Yorkshire Urgent & Emergency Care) Vanguard or alternative sources to implement the ‘Safe Haven’ model. For C&YP – to consider what services could offer a late afternoon, early evening and weekend, including consideration of a digital response |  | Fiona Venner Leeds Survivor Led Crisis Service Jim Leyland Leeds Touchstone Judith Barnes Clinical Operations Manager Crisis Assessment Service LYPFT Jenny Thornton Programme Manager Mental Health Leeds CCG’s | To offer a more appropriate venue for individuals with an emerging mental health crisis to access support and early intervention. To reduce the number of avoidable attendances at the Emergency Departments. To reduce the number of avoidable attendances at the Emergency Department. | Leeds crisis café funding secured from WY UC Vanguard launched Nov 16 . C & YP response being picked up - see above | Leeds crisis café in implementation phase. C & YP response being picked up by CYP workstream- see above | A & D
24/7 Access to services To improve the accessibility and quality of emotional support and information available both on-line and via telephone to those in mental distress. To reduce the number of out of area placements for acute in-patient episodes. | To understand the current level of emotional support and information and what would be required to enhance existing provision across the city. To address the gaps in provision that would enable the delivery of culturally sensitive and culturally competent services. To improve online information regarding how to access services in a mental health crisis via the Information Portal. To ensure that an EMH (Emotional Mental Health) assessment is undertaken within 4 hours for CYP presenting in mental health crisis to emergency department, 24 hours a day. To review the acute alternative to hospital model within LYPFT (Leeds and York Partnership NHS Foundation Trust) and with NHSE (England) for inpatient beds for CYP. To ensure any local bed management projects are aligned to the WYUEC (West Yorkshire Urgent & Emergency Care) Vanguard MH workstream |  | Jenny Thornton MH Programme Manager Leeds CCG’s Jeanette Lawson Capacity & Flow manager LYPFT Alicia Ridout Project manager Information Portal MH Framework Programme, Leeds CCG’s. Ruth Gordon Programme Manager for Children and Maternity Services, Leeds CCGs. Eve Townsley Locality Manager LPFT | To ensure appropriate services are accessible 24/7 for individuals and carers for people with an emerging or acute mental health crisis. To empower existing users of mental health services and the general public to employ self-management techniques and be better able to navigate services. Improved access to crisis care and reduced inappropriate referrals and delays in accessing assessment To ensure acute care is delivered as close to home as possible, minimising disruption and inconvenience to service users and families. | MindWell MH Information portal launched Oct 16. "I need help now" and self management resources within. | Core 24 funding pilot in implementation phase MindWell MH Information portal data collection shows website being frquently used for "I need help now" guidance . | A & D
Suicide Prevention To ensure there is a collaborrative approach across the city. | To continue to engage with the Suicide Prevention Strategy for the city. To develop a Leeds Mental Health provider suicide prevention strategy. To ensure all suicide prevention work is aligned to the WYUEC (West Yorkshire Urgent & Emergency Care) Vanguard workstream. To ensure there is adequate support for all affected by suicide (family, colleagues, carers, and clinicians). Ensure rapid access to services in case of self-harm or suicide attempts. Support staff in universal, targeted and specialist services to recognise signs of suicidal risks, intent and ideology and know how to access rapid support. |  | Catherine Ward Emotional Health and Wellbeing Lead The Office of the Director of Public Health Leeds City Council Anthony Deery Director of Nursing LYPFT Jane Mischenko, Commissioning Lead: Children & Maternity Services NHS Leeds CCGs Ruth Gordon Programme Manager for Children and Maternity Services, Leeds CCGs. | To reduce the number of suicides within Leeds. | LYPFT (Leeds and York Partnership NHS Foundation Trust) have set up a suicide prevention strategy steering group and are liaising with STP (Sustainability & Transformation Plan) lead as they develop their own. | New Leeds Suicide prevention strategy in development.will report in to HWB (Health & Wellbeing) Board and MH Partnership Board CW MindWell "I need help now" function and "Are you having suicidal thoughts?" Connect helpline, Dial House and Crisis café provide rapid access LYPFT Street triage, Police District Control Room nurses, Acute MH Liaison in LTHT (Leeds Teaching Hospitals) ED and crisis assessment unit Assist training | A & D
Inequalities in health Whilst recognising there are many inequalities across the city for the purpose of the CCC the initial focus is black and minority ethnic groups. To understand the Leeds experience of crisis pathway by BME communities and for that to inform work targeted at improving that experience. Figures suggest some black and minority ethnic groups are detained more frequently under the Mental Health Act. For CYP children who are Looked After, including Care Leavers, is the initial focus of work in 2016/17. | To improve data quality through contracts with providers. To pull together all the quantitative and qualitative intelligence available to evidence themes for black and minority ethnic groups to enable the development of culturally competent actions. Scoping work is ongoing to look at how we support these young people, including when they are in crisis |  | Caroline Bamford Head of Diversity & Inclusion LYPFT John Halsall Touchstone Community Health Development Analyst Catherine Williams, Commissioning Manager, LSE CCG | To understand the inequalities in the way people engage in services and then subsequently access mental health services in Leeds. To develop services to adequately meet the needs of the local population. | BAME working group | PAFRAS (Positive Action for Refugees & Asylum Seekers) engaged with crisis pathway development Crisis cafe engaging with people from BAME Leeds Mental Health Needs Asessment in final draft stage. BAME working group established and audit of crisis admissions to LYPFT. Further audit work now in place to measure the use of MHA for this group. | A & D
Carers To recognise the role carers play in supporting individuals experiencing mental health needs. | To meet with the Carers Commissioning Lead for Leeds to further understanding of any gaps in the concordat. To ensure the Carers strategy is reflected within Commissioning Intentions for Leeds To consult with carers regarding the specific appropriate actions required to help them support the person and cope well at times of emerging and acute mental health crisis. Support LYPFT (Leeds and York Partnership NHS Foundation Trust) services to introduce Triangle of Care principles into practice To ensure that young carers are considered as part of the all age work. |  | Jenny Thornton MH Programme Manager Leeds CCG’s Steve Taylor/Lou Bergin Triangle of Care Coordinators Carers Leeds Ruth Gordon Programme Manager for Children and Maternity Services, Leeds CCGs. | To recognise the role carers play in supporting individuals experiencing mental health needs. To recognise the impact mental health of the adults around a CYP, particularly parents, can have on young people. | Consult with carers regarding the specific appropriate actions required to help them support the person and cope well at times of emerging and acute mental health crisis complete | MIndWell "I am concerned about someone else" section now live. Carers section contains 16 25 years information . Mindmate parent and carers section live. LYPFT (Leeds and York Partnership NHS Foundation Trust) Support Carer Better CQUIN (Commissioning for Quality and Innovation) target 2017-18 – co-production approach with carers. Triange of care 2018-19 focus will move to crisis, | A & D
Dual Diagnosis To ensure DD priorities are fully recognised and embedded within relevant city-wide strategies and frameworks To have processes and pathways in place that provide effective access and support for people with co-existing drug use and mental health needs | Influence and support where appropriate by contributing to key work streams under the MH Framework Implement and report against achievement of DD (Dual Diagnosis) actions within the Leeds D&A (Drugs & Alcohol) Strategy and Action Plan Develop a better understanding around the effectiveness of the current crisis care pathway for people with DD in order to address any gaps or barriers Ensure timely access to appropriate assessment, treatment and support for people with DD needs, regardless of where they present in the system All staff within relevant services are trained in line with DD Capability Framework for Leeds Maintain and continue to promote best practice through the DD Network Ensure all relevant agencies are represented. Ensure meaningful and effective service user involvement in the development, implementation and review of city wide DD priorities with specific engagement around: • Design and delivery of training for front line services • Representation at all levels within DD Project • Work to challenge and address attitudes and stigma towards DD Support the development of the MH information portal to ensure that this is sufficiently tailored towards the needs of people with DD (Dual Diagnosis) Engage with existing support groups and other relevant stakeholders to undertake a review of DD peer support provision and actively contribute to citywide peer support initiatives. To ensure that services for young people are included in the all age work. |  | Dawn Bray Commissioning Programme Leader. The Office of the Director of Public Health Leeds City Council Karen Pearse Dual Diagnosis Project Manager St Anne's Community Services Anne Hobbs Forward Leeds Eddie Devine Service manager LYPFT (Leeds and York Partnership NHS Foundation Trust) Ruth Gordon Programme Manager for Children and Maternity Services, Leeds CCGs. | Improved outcomes for individuals that have co-existing substance use and mental health needs Improved access and support for individuals with DD Less people with DD reaching crisis point and requiring admission to hospital as a result of timely and effective support in the community Competent workforce equipped with skills and knowledge to recognise and meet the needs of clients with DD Lead practitioners are embedded within all mental health and substance use services as well as wider support services eg housing Improved experience and outcomes for DD service users based on feedback DD peer support is embedded within the redesign and development of community MH and substance use services Enhanced offer and provision of DD peer support through the Leeds Mind Peer Support Hub | LYPFT (Leeds and York Partnership NHS Foundation Trust) DD training ZIP SU enagagement in service development including MindWell information portal | Dual diagnosis YP lead engaged with Transitions workstream to ensure that services for young people are included in the all age work. | ABC&D
24/7 Access to services To reduce the number of out of area placements for acute in-patient episodes | LYPFT (Leeds and York Partnership NHS Foundation Trust) review of Intensive Community Services |  |  |  | Development of joint escaltion process LTHT (Leeds Teaching Hospitals) & LYPFT (Leeds and York Partnership NHS Foundation Trust). Positive Evaluation of imapct of High Volume Service Users project on fequent attenders/ users of emergency services | High Volume Service Users project re commissioned for 2017/18. LYPFT (Leeds and York Partnership NHS Foundation Trust) review of Intensive Community Services. Management of OAPS within LYPFT has produced reduction in usage Joint escaltion process LTHT (Leeds Teaching Hospitals) & LYPFT complete | B & C