## Action Plan
Crisis Care Concordat Action Plan
• Commissioning to allow earlier intervention and responisve crisis services • Access to support before a crisis • Urgent and emergency access to care • Quality of care and treatment in a crisis • Recovery and staying well
Red | not on track and needs urgent intervention
Amber | in progress
Green | complete
| Action | Owner | detail | Timescale | Update -progress | RAG Rating
Develop evidence-based crisis and urgent care pathways for mental health that are 24/7 | Map the urgent and crisis pathway | RK | Identify stakeholders Arrange workshop Identify process identify gaps | 2017-12-01
| Engagement of people with lived experience - commissioning for co-production |  | People with lived experience need to be part of the mapping process Develop high level pathway/process for all stakeholders to agree to | 2017-12-01
Review models of crisis service provision - including street triage, PDU, ambulance first responder scheme, models of best practice/innovation
| Review Liaison mental health in acute hospitals | RK | Is it fit for purose? Does it need to be 24/24 Does it report FROM LP outcome measures
Review CRHT in line with CORE as per IAF
| Review 136 and HPoS process |  | Data collection Analysis process mapping Alternatives
| Review acute pathway |  | SSSFT leading on will report to MHCCC
| Children and young people’s community crisis response and liaison mental health in acute hospitals. | AH | New service to commence | 2017-05-01
Suicide prevention strategy | Link to the suicide prevention action plan | Public Health | Joint suicide prevention strategy acrosss S, T&W in draft form out for wider commicuantion from the suicide prevention netweork | TBC
Adult primary prevention | Scope and implement a programme of work to improve provision of community mental health care, delivering evidence based treatment pathways for a range of conditions, from referral through to recovery. Taken from 2.2.of national signaturies | FS | extend scope of iapt with the inclusion of LTC (T&W) | April
|  | RK | review and redesign GP counsellors to ensure equity of service delivery (Shrop) | May
Scope use of 111 | Ensure 111 is suitable for use in mental health urgent and crisis situations |  | Is the 111 service useful for prevention or access to mental health support? Ensure that the DOS has the most uptodate information
Alternativce to 136 | Implement an alterntive safe place for people in mental distress as an alternvaitve to 136 | FS / RK | Implement the Branches and the Sanctuary | May
Crisis plans | For crisis plans or Wellness Recovery Action Plans to be in place for all people in contact with mental health services | SSSFT/LA providers/Voluntary sector
Community based recovery | Improving access to recovery opportunities in the community |  | Asset based approach - linking current providers in the community together to provide a web of service proviison to support people in recovery. Build on this to enhance the support available
Peer recovery in the community

## IAF targets
Improvement and Assessment Framework
Crisis care |  | Compliant / non complaint | Comments and actions
1a | Are the CCG and Provider implementing an agreed and funded service development and improvement plan to ensure that the adult component of the local acute hospital liaison mental health service is staffed to deliver, as a minimum, the ‘Core 24’ service specification by 20/21? |  | Currently the RAID service operates 24/7 from aged 16 onwards.
1b | Are the CCG and Provider implementing an agreed and funded service development and improvement plan for a dedicated mental health crisis and liaison response for children and young people presenting to emergency departments, in wards and community settings which includes provision for a response across extended hours? (This may be provided as a specific CYP crisis team, life course/all ages provision or/and a multi-agency response). |  | However due to the size of the hospital this may not be viable to continue
1c | Is the liaison service commissioned to provide an on-site 24/7 service? (adults) |  | yes
1d | Is the liaison service commissioned to provide a 1 hour response time following an Emergency Department referral and 24 hour response time following a ward referral? |  | yes
1e | Is the commissioned liaison service routinely collecting outcome measures in line with the RCPsych standards for adults (FROM-LP)?
Crisis Resolution and Home Treatment Teams |  | Compliant / non complaint | Comments and actions
2a | Are the CCG and Provider implementing an agreed and funded service development and improvement plan to ensure the CRHTT is operating effectively and in line with recognised best practice? Partially compliant |  | The service has benchmarked itself against CORE fidelity criteria in 2013. There is some discrepancy as to which standards / best practice it refers to i.e. HTAS or CORE. However, work is underway to updating the CORE fidelity work to see if there has been any improvements an improvement plan will follow
2b | Is the CRHTT commissioned to respond quickly to new referrals, providing a 24/7 "gatekeeping" function for acute inpatient beds, assessing all people face to face within four hours of referral? |  | yes
2c | Is the CRHTT staffed adequately, with caseloads in line with recommended practice? |  | As comment in 2a
2d | Is the commissioned CRHTT offering intensive home treatment in line with recommended practice? (For example, by routinely visiting people at least twice a day the first three days of home treatment, providing twice daily visits when required thereafter, and routinely offering visits that allow enough time to prioritise therapeutic relationships and help with social and practical problems) |  | As comment in 2a
2e | Does the commissioned CRHTT routinely collect and monitor clinician and patient reported outcomes, as well as feedback from people who use the service? |  | There is routine collection of data as well as service user comments captured, however this requires further embedding
Places of Safety |  | Compliant / non complaint | Comments and actions
3a | Does the CCG (individually or collaboratively with other CCGs) commission 24/7 accessible health-based places of safety which operate in such a way that people of any age do not have to undergo a Mental Health Act section 136 (s136) assessment in police custody? |  | Yes – although here is pressure to commission an additional 136 suite. Decommissioning PATH house to create a pilot of a crisis crash pad model will go some way to providing an alternative place to avert crisis however without a systems approach to redesigning crisis care there is the potential to repeat history by developing things in a piecemeal way.
3b | Does the CCG actively use provider, police and local authority data to monitor and understand the demand for health-based places of safety, as well as outcomes for s136 detainees?
3c | Is the CCG party/signatory to a joint s136 protocol with other local partners as per the Mental Health Act Code of Practice, which is regularly reviewed with a clear action plan to address any concerns? |  | The Mental Health Crisis Care Concordat (MHCCC) has just been re-launched. There is a 136 protocol which currently the CCG is not a signatory to. The protocol will be reviewed.
3d | Do senior CCG representatives actively instigate a joint incident review whenever someone detained under s136 within your geographical footprint is refused access to a health-based place of safety and/or taken to police custody? Not compliant |  | Further to the comment in 3c the review of the protocol will look at including senior CCG representative instigate a joint review.
3e | Does the CCG (individually or jointly e.g. with a Police & Crime Commissioner) commission services from a provider which give police officers urgent access to mental health specialist clinical advice Fully compliant |  | This is fully complaint because we have a crisis resolution and home treatment team CR/HT and the police can access them for clinical advice. However the model that is most effective in reducing 136’s is to have mental health nurses, as part of the police district call centre who can advise and intercept resulting in the CR/HT being sent out to the incident and not the police
Out of Area Treatment |  | Compliant / non complaint | Comments and actions
1 | Has the CCG established a process to monitor Mental Health out of area placements by bed type, which includes (at individual patient level) : i. how many out of area placements are made? ii. the reasons for out of area placements? iii. the duration of out of area placements? iv. the cost of out of area placements? |  | We receive weekly reports on out of area placements, including PICU and out of area PICU.
2 | Does the CCG have a plan in place to reduce the use of all types of mental health out of area placements for which it has commissioning responsibilities, with a specific focus on placements for non-specialist acute mental health beds during 2016/17? |  | There is not a formal written down plan however current custom and practice is about reducing all out of area placements. And when there is someone placed out of area they are repatriated as soon as possible.
3 | Can the CCG demonstrate that it is on track to deliver a reduction in the use of non-specialist acute mental health bed out of area placements by quarter 4 2016/17? |  | Yes There has been a reduction in out of area placements
Children and young people’s mental health |  | Compliant / non complaint | Comments and actions
1 | Has the CCG working with partners updated and re published the assured local transformation plan (LTP) from 2015/16 which includes baseline data? |  | The LTP has been updated and sent to NHS England for comment; it is due to be submitted 31st October
2 | Is the dedicated community eating disorder service commissioned by the CCG providing a service in line with the model recommended in the access and waiting time and commissioning guidance? Possible Answers: |  | The eating disorder service is now an all age service. SSSFT sub-contract to the Community Trust to deliver the CYP eating disorder service
3 | Is the Children and Young People’s Eating Disorder Team commissioned by the CCG part of a quality assurance network? Possible Answers: |  | The present service is not a member of a quality assurance network. Will need to ensure the 0-25 wellbeing service is
4 | Does the CCG have collaborative commissioning plans in place with NHS England for tier 3 and tier 4 CAMHS? (It is expected that all CCGs will have this in place by the end of December 2016) Possible Answers:
5 | Has the CCG published joint agency workforce plans detailing how they will build capacity and capability including implementation of Children and Young People’s Improving Access to Psychological Therapies programmes (CYP IAPT) transformation objectives? Possible Answers: